## Projects_plans
Project_ID | Phase | Start Date | Planned_Duration | Planned_Cost
1 | Phase 1 - Planning | 2018-01-16 | 196 | 50000
1 | Phase 2 - Initiation | 2018-01-31 | 15 | 100000
1 | Phase 3 - Implementation | 2018-04-17 | 197 | 150000
1 | Phase 4 - Manufacturing | 2018-10-10 | 61 | 450000
2 | Phase 1 - Planning | 2018-01-30 | 16 | 100000
2 | Phase 2 - Initiation | 2018-04-01 | 109 | 200000
2 | Phase 3 - Implementation | 2018-06-06 | 146 | 300000
2 | Phase 4 - Manufacturing | 2018-08-18 | 94 | 900000
3 | Phase 1 - Planning | 2018-03-03 | 91 | 50000
3 | Phase 2 - Initiation | 2018-03-25 | 77 | 100000
3 | Phase 3 - Implementation | 2018-04-28 | 169 | 150000
3 | Phase 4 - Manufacturing | 2018-10-23 | 61 | 450000
4 | Phase 1 - Planning | 2018-04-02 | 31 | 50000
4 | Phase 2 - Initiation | 2018-09-21 | 13 | 100000
4 | Phase 3 - Implementation | 2018-11-06 | 63 | 150000
4 | Phase 4 - Manufacturing | 2019-04-02 | 44 | 450000
5 | Phase 1 - Planning | 2018-01-19 | 11 | 50000
5 | Phase 2 - Initiation | 2018-02-13 | 167 | 100000
5 | Phase 3 - Implementation | 2018-03-05 | 197 | 150000
5 | Phase 4 - Manufacturing | 2018-05-06 | 60 | 450000
6 | Phase 1 - Planning | 2018-05-02 | 62 | 50000
6 | Phase 2 - Initiation | 2018-06-28 | 158 | 100000
6 | Phase 3 - Implementation | 2018-07-18 | 68 | 150000
6 | Phase 4 - Manufacturing | 2018-10-15 | 30 | 450000
7 | Phase 1 - Planning | 2018-02-16 | 190 | 100000
7 | Phase 2 - Initiation | 2018-04-08 | 15 | 200000
7 | Phase 3 - Implementation | 2018-06-06 | 162 | 300000
7 | Phase 4 - Manufacturing | 2018-10-27 | 78 | 900000
8 | Phase 1 - Planning | 2018-04-16 | 48 | 100000
8 | Phase 2 - Initiation | 2018-07-31 | 179 | 200000
8 | Phase 3 - Implementation | 2018-10-07 | 7 | 300000
8 | Phase 4 - Manufacturing | 2018-12-08 | 79 | 900000
9 | Phase 1 - Planning | 2018-01-27 | 173 | 100000
9 | Phase 2 - Initiation | 2018-02-28 | 66 | 200000
9 | Phase 3 - Implementation | 2018-04-21 | 9 | 300000
9 | Phase 4 - Manufacturing | 2018-06-04 | 98 | 900000
10 | Phase 1 - Planning | 2018-02-01 | 95 | 33333.3333
10 | Phase 2 - Initiation | 2018-06-13 | 17 | 66666.6667
10 | Phase 3 - Implementation | 2018-11-24 | 46 | 100000
10 | Phase 4 - Manufacturing | 2019-04-04 | 13 | 300000
11 | Phase 1 - Planning | 2018-04-19 | 55 | 100000
11 | Phase 2 - Initiation | 2018-08-04 | 6 | 200000
11 | Phase 3 - Implementation | 2018-08-24 | 107 | 300000
11 | Phase 4 - Manufacturing | 2019-02-08 | 48 | 900000
12 | Phase 1 - Planning | 2018-03-10 | 11 | 50000
12 | Phase 2 - Initiation | 2018-06-04 | 134 | 100000
12 | Phase 3 - Implementation | 2018-11-04 | 148 | 150000
12 | Phase 4 - Manufacturing | 2019-03-28 | 148 | 450000
13 | Phase 1 - Planning | 2018-02-13 | 89 | 50000
13 | Phase 2 - Initiation | 2018-05-30 | 192 | 100000
13 | Phase 3 - Implementation | 2018-09-04 | 125 | 150000
13 | Phase 4 - Manufacturing | 2019-01-21 | 176 | 450000
14 | Phase 1 - Planning | 2018-04-13 | 191 | 50000
14 | Phase 2 - Initiation | 2018-04-28 | 131 | 100000
14 | Phase 3 - Implementation | 2018-05-02 | 1 | 150000
14 | Phase 4 - Manufacturing | 2018-09-24 | 136 | 450000
15 | Phase 1 - Planning | 2018-01-01 | 166 | 33333.3333
15 | Phase 2 - Initiation | 2018-01-19 | 159 | 66666.6667
15 | Phase 3 - Implementation | 2018-07-09 | 26 | 100000
15 | Phase 4 - Manufacturing | 2018-09-28 | 110 | 300000
16 | Phase 1 - Planning | 2018-02-07 | 30 | 33333.3333
16 | Phase 2 - Initiation | 2018-05-21 | 101 | 66666.6667
16 | Phase 3 - Implementation | 2018-09-13 | 152 | 100000
16 | Phase 4 - Manufacturing | 2018-09-23 | 21 | 300000
17 | Phase 1 - Planning | 2018-01-07 | 140 | 100000
17 | Phase 2 - Initiation | 2018-04-14 | 174 | 200000
17 | Phase 3 - Implementation | 2018-06-20 | 110 | 300000
17 | Phase 4 - Manufacturing | 2018-11-14 | 72 | 900000
18 | Phase 1 - Planning | 2018-04-04 | 89 | 33333.3333
18 | Phase 2 - Initiation | 2018-06-07 | 178 | 66666.6667
18 | Phase 3 - Implementation | 2018-08-11 | 34 | 100000
18 | Phase 4 - Manufacturing | 2018-09-21 | 119 | 300000
19 | Phase 1 - Planning | 2018-03-17 | 186 | 100000
19 | Phase 2 - Initiation | 2018-04-05 | 115 | 200000
19 | Phase 3 - Implementation | 2018-09-07 | 184 | 300000
19 | Phase 4 - Manufacturing | 2018-12-26 | 145 | 900000
20 | Phase 1 - Planning | 2018-01-25 | 125 | 50000
20 | Phase 2 - Initiation | 2018-02-15 | 117 | 100000
20 | Phase 3 - Implementation | 2018-05-10 | 54 | 150000
20 | Phase 4 - Manufacturing | 2018-08-17 | 120 | 450000
21 | Phase 1 - Planning | 2018-04-13 | 49 | 50000
21 | Phase 2 - Initiation | 2018-06-06 | 60 | 100000
21 | Phase 3 - Implementation | 2018-11-23 | 151 | 150000
21 | Phase 4 - Manufacturing | 2019-03-09 | 177 | 450000
22 | Phase 1 - Planning | 2018-03-06 | 175 | 50000
22 | Phase 2 - Initiation | 2018-04-05 | 149 | 100000
22 | Phase 3 - Implementation | 2018-08-08 | 198 | 150000
22 | Phase 4 - Manufacturing | 2018-10-01 | 109 | 450000
23 | Phase 1 - Planning | 2018-04-26 | 151 | 100000
23 | Phase 2 - Initiation | 2018-06-22 | 16 | 200000
23 | Phase 3 - Implementation | 2018-09-09 | 67 | 300000
23 | Phase 4 - Manufacturing | 2019-01-22 | 14 | 900000
24 | Phase 1 - Planning | 2018-03-03 | 165 | 50000
24 | Phase 2 - Initiation | 2018-04-21 | 125 | 100000
24 | Phase 3 - Implementation | 2018-08-31 | 132 | 150000
24 | Phase 4 - Manufacturing | 2018-10-24 | 189 | 450000
25 | Phase 1 - Planning | 2018-02-05 | 20 | 33333.3333
25 | Phase 2 - Initiation | 2018-03-07 | 188 | 66666.6667
25 | Phase 3 - Implementation | 2018-03-15 | 102 | 100000
25 | Phase 4 - Manufacturing | 2018-05-17 | 105 | 300000
26 | Phase 1 - Planning | 2018-05-23 | 76 | 100000
26 | Phase 2 - Initiation | 2018-10-18 | 28 | 200000
26 | Phase 3 - Implementation | 2019-01-08 | 128 | 300000
26 | Phase 4 - Manufacturing | 2019-01-20 | 3 | 900000
27 | Phase 1 - Planning | 2018-02-19 | 60 | 50000
27 | Phase 2 - Initiation | 2018-06-13 | 199 | 100000
27 | Phase 3 - Implementation | 2018-11-11 | 57 | 150000
27 | Phase 4 - Manufacturing | 2018-12-09 | 125 | 450000
28 | Phase 1 - Planning | 2018-01-24 | 21 | 100000
28 | Phase 2 - Initiation | 2018-06-08 | 94 | 200000
28 | Phase 3 - Implementation | 2018-07-29 | 128 | 300000
28 | Phase 4 - Manufacturing | 2018-08-26 | 91 | 900000
29 | Phase 1 - Planning | 2018-03-08 | 7 | 50000
29 | Phase 2 - Initiation | 2018-07-26 | 80 | 100000
29 | Phase 3 - Implementation | 2018-09-07 | 117 | 150000
29 | Phase 4 - Manufacturing | 2019-01-01 | 5 | 450000
30 | Phase 1 - Planning | 2018-01-07 | 165 | 100000
30 | Phase 2 - Initiation | 2018-02-11 | 182 | 200000
30 | Phase 3 - Implementation | 2018-03-01 | 17 | 300000
30 | Phase 4 - Manufacturing | 2018-03-31 | 149 | 900000
31 | Phase 1 - Planning | 2018-04-12 | 26 | 100000
31 | Phase 2 - Initiation | 2018-06-13 | 76 | 200000
31 | Phase 3 - Implementation | 2018-11-10 | 94 | 300000
31 | Phase 4 - Manufacturing | 2019-01-03 | 86 | 900000
32 | Phase 1 - Planning | 2018-02-28 | 107 | 50000
32 | Phase 2 - Initiation | 2018-03-09 | 76 | 100000
32 | Phase 3 - Implementation | 2018-04-03 | 134 | 150000
32 | Phase 4 - Manufacturing | 2018-07-20 | 34 | 450000
33 | Phase 1 - Planning | 2018-03-31 | 53 | 50000
33 | Phase 2 - Initiation | 2018-06-04 | 87 | 100000
33 | Phase 3 - Implementation | 2018-06-16 | 45 | 150000
33 | Phase 4 - Manufacturing | 2018-10-04 | 121 | 450000
34 | Phase 1 - Planning | 2018-05-26 | 109 | 100000
34 | Phase 2 - Initiation | 2018-07-03 | 153 | 200000
34 | Phase 3 - Implementation | 2018-07-06 | 165 | 300000
34 | Phase 4 - Manufacturing | 2018-11-15 | 181 | 900000
35 | Phase 1 - Planning | 2018-03-02 | 25 | 100000
35 | Phase 2 - Initiation | 2018-04-01 | 195 | 200000
35 | Phase 3 - Implementation | 2018-07-06 | 54 | 300000
35 | Phase 4 - Manufacturing | 2018-09-21 | 79 | 900000
36 | Phase 1 - Planning | 2018-02-25 | 54 | 50000
36 | Phase 2 - Initiation | 2018-07-13 | 66 | 100000
36 | Phase 3 - Implementation | 2018-12-17 | 63 | 150000
36 | Phase 4 - Manufacturing | 2019-05-10 | 176 | 450000
37 | Phase 1 - Planning | 2018-01-24 | 19 | 50000
37 | Phase 2 - Initiation | 2018-06-01 | 110 | 100000
37 | Phase 3 - Implementation | 2018-08-15 | 137 | 150000
37 | Phase 4 - Manufacturing | 2018-11-15 | 119 | 450000
38 | Phase 1 - Planning | 2018-04-22 | 135 | 50000
38 | Phase 2 - Initiation | 2018-05-30 | 48 | 100000
38 | Phase 3 - Implementation | 2018-08-22 | 171 | 150000
38 | Phase 4 - Manufacturing | 2019-01-04 | 47 | 450000
39 | Phase 1 - Planning | 2018-02-16 | 38 | 100000
39 | Phase 2 - Initiation | 2018-07-26 | 173 | 200000
39 | Phase 3 - Implementation | 2018-12-21 | 21 | 300000
39 | Phase 4 - Manufacturing | 2019-04-21 | 162 | 900000
40 | Phase 1 - Planning | 2018-04-28 | 142 | 33333.3333
40 | Phase 2 - Initiation | 2018-05-19 | 91 | 66666.6667
40 | Phase 3 - Implementation | 2018-09-17 | 175 | 100000
40 | Phase 4 - Manufacturing | 2018-12-16 | 54 | 300000
41 | Phase 1 - Planning | 2018-05-05 | 53 | 100000
41 | Phase 2 - Initiation | 2018-07-28 | 89 | 200000
41 | Phase 3 - Implementation | 2018-08-18 | 74 | 300000
41 | Phase 4 - Manufacturing | 2018-08-22 | 140 | 900000
42 | Phase 1 - Planning | 2018-05-27 | 194 | 50000
42 | Phase 2 - Initiation | 2018-08-28 | 183 | 100000
42 | Phase 3 - Implementation | 2018-11-22 | 166 | 150000
42 | Phase 4 - Manufacturing | 2019-01-24 | 33 | 450000
43 | Phase 1 - Planning | 2018-02-24 | 4 | 100000
43 | Phase 2 - Initiation | 2018-05-18 | 151 | 200000
43 | Phase 3 - Implementation | 2018-08-18 | 187 | 300000
43 | Phase 4 - Manufacturing | 2018-12-25 | 81 | 900000
44 | Phase 1 - Planning | 2018-02-27 | 117 | 50000
44 | Phase 2 - Initiation | 2018-04-07 | 126 | 100000
44 | Phase 3 - Implementation | 2018-04-19 | 71 | 150000
44 | Phase 4 - Manufacturing | 2018-10-02 | 113 | 450000
45 | Phase 1 - Planning | 2018-04-25 | 139 | 33333.3333
45 | Phase 2 - Initiation | 2018-09-26 | 193 | 66666.6667
45 | Phase 3 - Implementation | 2018-11-25 | 56 | 100000
45 | Phase 4 - Manufacturing | 2019-01-15 | 149 | 300000
46 | Phase 1 - Planning | 2018-04-20 | 10 | 50000
46 | Phase 2 - Initiation | 2018-08-27 | 60 | 100000
46 | Phase 3 - Implementation | 2019-02-19 | 184 | 150000
46 | Phase 4 - Manufacturing | 2019-06-05 | 200 | 450000
47 | Phase 1 - Planning | 2018-01-31 | 54 | 33333.3333
47 | Phase 2 - Initiation | 2018-03-12 | 152 | 66666.6667
47 | Phase 3 - Implementation | 2018-09-08 | 90 | 100000
47 | Phase 4 - Manufacturing | 2018-12-04 | 49 | 300000
48 | Phase 1 - Planning | 2018-04-08 | 66 | 100000
48 | Phase 2 - Initiation | 2018-05-05 | 110 | 200000
48 | Phase 3 - Implementation | 2018-08-03 | 178 | 300000
48 | Phase 4 - Manufacturing | 2018-08-22 | 167 | 900000
49 | Phase 1 - Planning | 2018-04-19 | 30 | 50000
49 | Phase 2 - Initiation | 2018-10-08 | 84 | 100000
49 | Phase 3 - Implementation | 2018-11-18 | 186 | 150000
49 | Phase 4 - Manufacturing | 2019-01-27 | 86 | 450000
50 | Phase 1 - Planning | 2018-05-27 | 158 | 50000
50 | Phase 2 - Initiation | 2018-07-28 | 136 | 100000
50 | Phase 3 - Implementation | 2018-09-22 | 121 | 150000
50 | Phase 4 - Manufacturing | 2018-11-01 | 129 | 450000
51 | Phase 1 - Planning | 2018-02-05 | 129 | 100000
51 | Phase 2 - Initiation | 2018-05-24 | 138 | 200000
51 | Phase 3 - Implementation | 2018-07-06 | 31 | 300000
51 | Phase 4 - Manufacturing | 2018-12-11 | 76 | 900000
52 | Phase A - Initiation | 2020-03-12 | 139 | 700
52 | Phase B - Preparation | 2020-06-29 | 157 | 16100
52 | Phase C - Development | 2020-08-04 | 9 | 21000
52 | Phase D - Testing | 2020-12-19 | 48 | 5600
52 | Phase E - Deployment | 2021-03-14 | 161 | 0
52 | Phase F - Post-deployment | 2021-07-06 | 26 | 2800
53 | Phase A - Initiation | 2020-04-23 | 38 | 700
53 | Phase B - Preparation | 2020-06-06 | 61 | 16100
53 | Phase C - Development | 2020-10-11 | 39 | 21000
53 | Phase D - Testing | 2020-12-30 | 15 | 5600
53 | Phase E - Deployment | 2021-02-14 | 124 | 0
53 | Phase F - Post-deployment | 2021-06-21 | 111 | 2800
54 | Phase A - Initiation | 2020-05-20 | 173 | 700
54 | Phase B - Preparation | 2020-06-17 | 29 | 16100
54 | Phase C - Development | 2020-11-16 | 64 | 21000
54 | Phase D - Testing | 2021-01-24 | 173 | 5600
54 | Phase E - Deployment | 2021-06-25 | 52 | 0
54 | Phase F - Post-deployment | 2021-09-12 | 184 | 2800
55 | Phase A - Initiation | 2020-01-15 | 68 | 700
55 | Phase B - Preparation | 2020-02-28 | 161 | 16100
55 | Phase C - Development | 2020-07-17 | 66 | 21000
55 | Phase D - Testing | 2020-08-17 | 153 | 5600
55 | Phase E - Deployment | 2020-10-20 | 83 | 0
55 | Phase F - Post-deployment | 2021-01-17 | 19 | 2800
56 | Phase A - Initiation | 2020-02-07 | 154 | 700
56 | Phase B - Preparation | 2020-02-15 | 47 | 16100
56 | Phase C - Development | 2020-05-28 | 95 | 21000
56 | Phase D - Testing | 2020-09-21 | 12 | 5600
56 | Phase E - Deployment | 2020-12-23 | 160 | 0
56 | Phase F - Post-deployment | 2021-06-14 | 124 | 2800
57 | Phase A - Initiation | 2020-05-04 | 157 | 700
57 | Phase B - Preparation | 2020-10-16 | 117 | 16100
57 | Phase C - Development | 2021-03-30 | 127 | 21000
57 | Phase D - Testing | 2021-05-02 | 25 | 5600
57 | Phase E - Deployment | 2021-09-08 | 65 | 0
57 | Phase F - Post-deployment | 2021-11-03 | 200 | 2800
58 | Phase A - Initiation | 2020-04-07 | 33 | 700
58 | Phase B - Preparation | 2020-06-21 | 73 | 16100
58 | Phase C - Development | 2020-10-02 | 187 | 21000
58 | Phase D - Testing | 2021-02-26 | 153 | 5600
58 | Phase E - Deployment | 2021-05-13 | 36 | 0
58 | Phase F - Post-deployment | 2021-09-26 | 183 | 2800
59 | Phase A - Initiation | 2020-03-07 | 18 | 350
59 | Phase B - Preparation | 2020-05-29 | 42 | 8050
59 | Phase C - Development | 2020-06-30 | 42 | 10500
59 | Phase D - Testing | 2020-11-15 | 121 | 2800
59 | Phase E - Deployment | 2021-03-23 | 85 | 0
59 | Phase F - Post-deployment | 2021-07-25 | 7 | 1400
60 | Phase A - Initiation | 2020-03-03 | 177 | 350
60 | Phase B - Preparation | 2020-05-27 | 30 | 8050
60 | Phase C - Development | 2020-11-01 | 80 | 10500
60 | Phase D - Testing | 2021-04-08 | 169 | 2800
60 | Phase E - Deployment | 2021-09-30 | 94 | 0
60 | Phase F - Post-deployment | 2021-10-28 | 151 | 1400
61 | Phase A - Initiation | 2020-01-05 | 122 | 700
61 | Phase B - Preparation | 2020-02-04 | 65 | 16100
61 | Phase C - Development | 2020-07-03 | 109 | 21000
61 | Phase D - Testing | 2020-07-07 | 1 | 5600
61 | Phase E - Deployment | 2020-07-13 | 99 | 0
61 | Phase F - Post-deployment | 2020-09-18 | 82 | 2800
62 | Phase A - Initiation | 2020-01-30 | 18 | 700
62 | Phase B - Preparation | 2020-03-06 | 94 | 16100
62 | Phase C - Development | 2020-03-09 | 151 | 21000
62 | Phase D - Testing | 2020-05-25 | 106 | 5600
62 | Phase E - Deployment | 2020-07-21 | 31 | 0
62 | Phase F - Post-deployment | 2020-10-09 | 31 | 2800
63 | Phase A - Initiation | 2020-03-07 | 60 | 700
63 | Phase B - Preparation | 2020-04-04 | 4 | 16100
63 | Phase C - Development | 2020-08-05 | 153 | 21000
63 | Phase D - Testing | 2020-12-26 | 85 | 5600
63 | Phase E - Deployment | 2021-01-24 | 176 | 0
63 | Phase F - Post-deployment | 2021-03-02 | 104 | 2800
64 | Phase A - Initiation | 2020-01-17 | 63 | 350
64 | Phase B - Preparation | 2020-03-29 | 16 | 8050
64 | Phase C - Development | 2020-08-03 | 198 | 10500
64 | Phase D - Testing | 2020-08-27 | 176 | 2800
64 | Phase E - Deployment | 2020-12-24 | 166 | 0
64 | Phase F - Post-deployment | 2021-06-06 | 193 | 1400
65 | Phase A - Initiation | 2020-05-24 | 104 | 350
65 | Phase B - Preparation | 2020-09-08 | 173 | 8050
65 | Phase C - Development | 2021-01-09 | 8 | 10500
65 | Phase D - Testing | 2021-04-01 | 14 | 2800
65 | Phase E - Deployment | 2021-05-27 | 29 | 0
65 | Phase F - Post-deployment | 2021-10-27 | 114 | 1400
66 | Phase A - Initiation | 2020-01-02 | 20 | 700
66 | Phase B - Preparation | 2020-05-13 | 160 | 16100
66 | Phase C - Development | 2020-07-09 | 79 | 21000
66 | Phase D - Testing | 2020-12-16 | 129 | 5600
66 | Phase E - Deployment | 2021-05-12 | 135 | 0
66 | Phase F - Post-deployment | 2021-09-29 | 195 | 2800
67 | Phase A - Initiation | 2020-01-05 | 14 | 350
67 | Phase B - Preparation | 2020-01-12 | 69 | 8050
67 | Phase C - Development | 2020-02-16 | 144 | 10500
67 | Phase D - Testing | 2020-04-20 | 140 | 2800
67 | Phase E - Deployment | 2020-07-25 | 135 | 0
67 | Phase F - Post-deployment | 2020-09-11 | 79 | 1400
68 | Phase A - Initiation | 2020-01-23 | 141 | 350
68 | Phase B - Preparation | 2020-07-01 | 164 | 8050
68 | Phase C - Development | 2020-07-19 | 70 | 10500
68 | Phase D - Testing | 2020-09-11 | 132 | 2800
68 | Phase E - Deployment | 2020-11-16 | 92 | 0
68 | Phase F - Post-deployment | 2021-03-15 | 109 | 1400
69 | Phase A - Initiation | 2020-05-31 | 197 | 700
69 | Phase B - Preparation | 2020-08-20 | 193 | 16100
69 | Phase C - Development | 2021-01-01 | 58 | 21000
69 | Phase D - Testing | 2021-06-07 | 91 | 5600
69 | Phase E - Deployment | 2021-08-26 | 27 | 0
69 | Phase F - Post-deployment | 2022-02-13 | 187 | 2800
70 | Phase A - Initiation | 2020-05-11 | 134 | 350
70 | Phase B - Preparation | 2020-08-17 | 191 | 8050
70 | Phase C - Development | 2020-12-25 | 35 | 10500
70 | Phase D - Testing | 2021-02-05 | 1 | 2800
70 | Phase E - Deployment | 2021-05-30 | 164 | 0
70 | Phase F - Post-deployment | 2021-11-17 | 60 | 1400
71 | Phase A - Initiation | 2020-03-11 | 135 | 350
71 | Phase B - Preparation | 2020-05-29 | 152 | 8050
71 | Phase C - Development | 2020-11-18 | 14 | 10500
71 | Phase D - Testing | 2020-12-28 | 125 | 2800
71 | Phase E - Deployment | 2021-02-10 | 95 | 0
71 | Phase F - Post-deployment | 2021-06-13 | 134 | 1400
72 | Phase A - Initiation | 2020-05-11 | 193 | 350
72 | Phase B - Preparation | 2020-05-26 | 113 | 8050
72 | Phase C - Development | 2020-06-01 | 86 | 10500
72 | Phase D - Testing | 2020-08-20 | 75 | 2800
72 | Phase E - Deployment | 2020-10-23 | 178 | 0
72 | Phase F - Post-deployment | 2020-12-27 | 3 | 1400
73 | Phase A - Initiation | 2020-05-05 | 127 | 350
73 | Phase B - Preparation | 2020-07-30 | 52 | 8050
73 | Phase C - Development | 2021-01-19 | 37 | 10500
73 | Phase D - Testing | 2021-05-09 | 52 | 2800
73 | Phase E - Deployment | 2021-07-21 | 53 | 0
73 | Phase F - Post-deployment | 2021-08-09 | 89 | 1400
74 | Phase A - Initiation | 2020-01-14 | 158 | 350
74 | Phase B - Preparation | 2020-05-23 | 123 | 8050
74 | Phase C - Development | 2020-07-20 | 181 | 10500
74 | Phase D - Testing | 2020-08-22 | 154 | 2800
74 | Phase E - Deployment | 2020-12-17 | 153 | 0
74 | Phase F - Post-deployment | 2021-02-15 | 172 | 1400
75 | Phase A - Initiation | 2020-03-20 | 8 | 700
75 | Phase B - Preparation | 2020-06-12 | 122 | 16100
75 | Phase C - Development | 2020-08-07 | 132 | 21000
75 | Phase D - Testing | 2020-12-09 | 104 | 5600
75 | Phase E - Deployment | 2021-02-20 | 110 | 0
75 | Phase F - Post-deployment | 2021-05-07 | 69 | 2800
76 | Phase A - Initiation | 2020-03-23 | 31 | 350
76 | Phase B - Preparation | 2020-09-14 | 196 | 8050
76 | Phase C - Development | 2021-01-12 | 145 | 10500
76 | Phase D - Testing | 2021-05-29 | 44 | 2800
76 | Phase E - Deployment | 2021-10-01 | 61 | 0
76 | Phase F - Post-deployment | 2022-02-06 | 78 | 1400
77 | Phase A - Initiation | 2020-03-27 | 11 | 350
77 | Phase B - Preparation | 2020-07-22 | 134 | 8050
77 | Phase C - Development | 2020-08-20 | 188 | 10500
77 | Phase D - Testing | 2020-12-30 | 99 | 2800
77 | Phase E - Deployment | 2021-06-08 | 166 | 0
77 | Phase F - Post-deployment | 2021-09-18 | 189 | 1400
78 | Phase A - Initiation | 2020-05-18 | 164 | 350
78 | Phase B - Preparation | 2020-10-05 | 101 | 8050
78 | Phase C - Development | 2021-02-10 | 38 | 10500
78 | Phase D - Testing | 2021-03-08 | 26 | 2800
78 | Phase E - Deployment | 2021-04-16 | 31 | 0
78 | Phase F - Post-deployment | 2021-10-11 | 99 | 1400
79 | Phase A - Initiation | 2020-02-05 | 127 | 700
79 | Phase B - Preparation | 2020-05-25 | 126 | 16100
79 | Phase C - Development | 2020-10-28 | 184 | 21000
79 | Phase D - Testing | 2021-01-08 | 123 | 5600
79 | Phase E - Deployment | 2021-02-26 | 122 | 0
79 | Phase F - Post-deployment | 2021-05-03 | 172 | 2800
80 | Phase A - Initiation | 2020-02-23 | 159 | 700
80 | Phase B - Preparation | 2020-04-02 | 186 | 16100
80 | Phase C - Development | 2020-05-05 | 198 | 21000
80 | Phase D - Testing | 2020-09-23 | 101 | 5600
80 | Phase E - Deployment | 2021-03-12 | 170 | 0
80 | Phase F - Post-deployment | 2021-05-21 | 131 | 2800
81 | Phase A - Initiation | 2020-05-28 | 113 | 700
81 | Phase B - Preparation | 2020-10-13 | 48 | 16100
81 | Phase C - Development | 2020-12-02 | 1 | 21000
81 | Phase D - Testing | 2021-05-03 | 53 | 5600
81 | Phase E - Deployment | 2021-10-13 | 168 | 0
81 | Phase F - Post-deployment | 2021-10-25 | 185 | 2800
82 | Phase A - Initiation | 2020-04-20 | 63 | 700
82 | Phase B - Preparation | 2020-06-24 | 174 | 16100
82 | Phase C - Development | 2020-07-07 | 20 | 21000
82 | Phase D - Testing | 2020-11-18 | 102 | 5600
82 | Phase E - Deployment | 2021-02-28 | 58 | 0
82 | Phase F - Post-deployment | 2021-04-05 | 194 | 2800
83 | Phase A - Initiation | 2020-03-07 | 41 | 233.3333
83 | Phase B - Preparation | 2020-07-14 | 124 | 5366.6667
83 | Phase C - Development | 2020-07-24 | 185 | 7000
83 | Phase D - Testing | 2020-09-02 | 112 | 1866.6667
83 | Phase E - Deployment | 2021-01-01 | 81 | 0
83 | Phase F - Post-deployment | 2021-06-05 | 174 | 933.3333
84 | Phase A - Initiation | 2020-01-27 | 191 | 233.3333
84 | Phase B - Preparation | 2020-03-31 | 46 | 5366.6667
84 | Phase C - Development | 2020-08-30 | 109 | 7000
84 | Phase D - Testing | 2021-01-15 | 30 | 1866.6667
84 | Phase E - Deployment | 2021-07-12 | 5 | 0
84 | Phase F - Post-deployment | 2021-11-11 | 115 | 933.3333
85 | Phase A - Initiation | 2020-03-14 | 187 | 350
85 | Phase B - Preparation | 2020-06-04 | 76 | 8050
85 | Phase C - Development | 2020-10-17 | 31 | 10500
85 | Phase D - Testing | 2021-02-12 | 123 | 2800
85 | Phase E - Deployment | 2021-07-07 | 109 | 0
85 | Phase F - Post-deployment | 2021-11-19 | 197 | 1400
86 | Phase A - Initiation | 2020-01-13 | 36 | 233.3333
86 | Phase B - Preparation | 2020-03-29 | 193 | 5366.6667
86 | Phase C - Development | 2020-08-04 | 109 | 7000
86 | Phase D - Testing | 2020-12-07 | 76 | 1866.6667
86 | Phase E - Deployment | 2021-01-29 | 92 | 0
86 | Phase F - Post-deployment | 2021-07-01 | 139 | 933.3333
87 | Phase A - Initiation | 2020-03-08 | 112 | 233.3333
87 | Phase B - Preparation | 2020-05-30 | 50 | 5366.6667
87 | Phase C - Development | 2020-09-26 | 96 | 7000
87 | Phase D - Testing | 2021-01-20 | 79 | 1866.6667
87 | Phase E - Deployment | 2021-06-09 | 183 | 0
87 | Phase F - Post-deployment | 2021-12-04 | 148 | 933.3333
88 | Phase A - Initiation | 2020-05-02 | 92 | 233.3333
88 | Phase B - Preparation | 2020-10-11 | 75 | 5366.6667
88 | Phase C - Development | 2021-01-22 | 96 | 7000
88 | Phase D - Testing | 2021-03-21 | 108 | 1866.6667
88 | Phase E - Deployment | 2021-08-14 | 77 | 0
88 | Phase F - Post-deployment | 2021-08-17 | 57 | 933.3333
89 | Phase A - Initiation | 2020-03-09 | 20 | 233.3333
89 | Phase B - Preparation | 2020-08-30 | 149 | 5366.6667
89 | Phase C - Development | 2021-02-16 | 103 | 7000
89 | Phase D - Testing | 2021-03-10 | 4 | 1866.6667
89 | Phase E - Deployment | 2021-06-11 | 152 | 0
89 | Phase F - Post-deployment | 2021-09-14 | 109 | 933.3333
90 | Phase A - Initiation | 2020-03-10 | 2 | 233.3333
90 | Phase B - Preparation | 2020-06-04 | 17 | 5366.6667
90 | Phase C - Development | 2020-11-27 | 52 | 7000
90 | Phase D - Testing | 2021-03-01 | 60 | 1866.6667
90 | Phase E - Deployment | 2021-08-03 | 182 | 0
90 | Phase F - Post-deployment | 2021-09-23 | 96 | 933.3333
91 | Phase A - Initiation | 2020-03-30 | 54 | 233.3333
91 | Phase B - Preparation | 2020-05-15 | 183 | 5366.6667
91 | Phase C - Development | 2020-09-16 | 129 | 7000
91 | Phase D - Testing | 2020-12-17 | 35 | 1866.6667
91 | Phase E - Deployment | 2021-03-04 | 144 | 0
91 | Phase F - Post-deployment | 2021-03-22 | 72 | 933.3333
92 | Phase A - Initiation | 2020-04-19 | 77 | 350
92 | Phase B - Preparation | 2020-07-24 | 45 | 8050
92 | Phase C - Development | 2020-12-04 | 191 | 10500
92 | Phase D - Testing | 2021-05-16 | 102 | 2800
92 | Phase E - Deployment | 2021-09-06 | 127 | 0
92 | Phase F - Post-deployment | 2021-10-15 | 126 | 1400
93 | Phase A - Initiation | 2020-03-22 | 41 | 350
93 | Phase B - Preparation | 2020-07-25 | 188 | 8050
93 | Phase C - Development | 2020-11-06 | 45 | 10500
93 | Phase D - Testing | 2021-01-05 | 159 | 2800
93 | Phase E - Deployment | 2021-06-13 | 104 | 0
93 | Phase F - Post-deployment | 2021-10-23 | 28 | 1400
94 | Phase A - Initiation | 2020-03-02 | 121 | 700
94 | Phase B - Preparation | 2020-05-08 | 16 | 16100
94 | Phase C - Development | 2020-06-22 | 110 | 21000
94 | Phase D - Testing | 2020-12-13 | 132 | 5600
94 | Phase E - Deployment | 2021-01-12 | 83 | 0
94 | Phase F - Post-deployment | 2021-01-22 | 46 | 2800
95 | Phase A - Initiation | 2020-04-05 | 28 | 350
95 | Phase B - Preparation | 2020-07-05 | 49 | 8050
95 | Phase C - Development | 2020-11-09 | 187 | 10500
95 | Phase D - Testing | 2020-12-24 | 93 | 2800
95 | Phase E - Deployment | 2021-03-18 | 96 | 0
95 | Phase F - Post-deployment | 2021-08-29 | 175 | 1400
96 | Phase A - Initiation | 2020-05-26 | 15 | 350
96 | Phase B - Preparation | 2020-08-07 | 75 | 8050
96 | Phase C - Development | 2020-10-14 | 161 | 10500
96 | Phase D - Testing | 2021-02-05 | 193 | 2800
96 | Phase E - Deployment | 2021-05-15 | 62 | 0
96 | Phase F - Post-deployment | 2021-06-08 | 80 | 1400
97 | Phase A - Initiation | 2020-02-05 | 86 | 350
97 | Phase B - Preparation | 2020-04-06 | 150 | 8050
97 | Phase C - Development | 2020-04-12 | 125 | 10500
97 | Phase D - Testing | 2020-06-27 | 53 | 2800
97 | Phase E - Deployment | 2020-09-15 | 134 | 0
97 | Phase F - Post-deployment | 2021-02-04 | 32 | 1400
98 | Phase A - Initiation | 2020-02-14 | 40 | 350
98 | Phase B - Preparation | 2020-08-05 | 116 | 8050
98 | Phase C - Development | 2020-09-11 | 147 | 10500
98 | Phase D - Testing | 2020-12-20 | 21 | 2800
98 | Phase E - Deployment | 2021-02-08 | 118 | 0
98 | Phase F - Post-deployment | 2021-06-27 | 143 | 1400
99 | Phase A - Initiation | 2020-04-15 | 64 | 350
99 | Phase B - Preparation | 2020-07-07 | 32 | 8050
99 | Phase C - Development | 2020-07-23 | 130 | 10500
99 | Phase D - Testing | 2020-09-15 | 102 | 2800
99 | Phase E - Deployment | 2020-10-21 | 134 | 0
99 | Phase F - Post-deployment | 2020-10-28 | 34 | 1400
100 | Phase A - Initiation | 2020-05-21 | 115 | 350
100 | Phase B - Preparation | 2020-06-22 | 190 | 8050
100 | Phase C - Development | 2020-07-07 | 92 | 10500
100 | Phase D - Testing | 2020-12-21 | 123 | 2800
100 | Phase E - Deployment | 2021-05-19 | 54 | 0
100 | Phase F - Post-deployment | 2021-05-28 | 32 | 1400
101 | Phase A - Initiation | 2020-01-16 | 121 | 700
101 | Phase B - Preparation | 2020-03-26 | 109 | 16100
101 | Phase C - Development | 2020-06-05 | 175 | 21000
101 | Phase D - Testing | 2020-11-27 | 68 | 5600
101 | Phase E - Deployment | 2021-02-21 | 2 | 0
101 | Phase F - Post-deployment | 2021-04-26 | 64 | 2800
102 | Phase A - Initiation | 2020-03-20 | 155 | 350
102 | Phase B - Preparation | 2020-05-24 | 3 | 8050
102 | Phase C - Development | 2020-06-02 | 199 | 10500
102 | Phase D - Testing | 2020-11-01 | 172 | 2800
102 | Phase E - Deployment | 2020-12-02 | 71 | 0
102 | Phase F - Post-deployment | 2021-04-30 | 12 | 1400
103 | Phase A - Initiation | 2020-05-09 | 9 | 350
103 | Phase B - Preparation | 2020-09-02 | 5 | 8050
103 | Phase C - Development | 2020-10-13 | 1 | 10500
103 | Phase D - Testing | 2021-01-06 | 102 | 2800
103 | Phase E - Deployment | 2021-02-06 | 175 | 0
103 | Phase F - Post-deployment | 2021-04-21 | 167 | 1400
104 | Phase 1 - Planning | 2018-05-12 | 186 | 50000
104 | Phase 2 - Initiation | 2018-06-07 | 185 | 100000
104 | Phase 3 - Implementation | 2018-06-23 | 72 | 150000
104 | Phase 4 - Manufacturing | 2018-12-08 | 191 | 450000

## Project type
Project_ID | Project Type
1 | Marketing - Launch of new product
2 | Marketing - Launch of new product
3 | Marketing - Launch of new product
4 | Marketing - Launch of new product
5 | Marketing - Launch of new product
6 | Marketing - Launch of new product
7 | Marketing - Launch of new product
8 | Marketing - Launch of new product
9 | Marketing - Launch of new product
10 | Marketing - Launch of new product
11 | Marketing - Launch of new product
12 | Marketing - Launch of new product
13 | Marketing - Launch of new product
14 | Marketing - Launch of new product
15 | Marketing - Launch of new product
16 | Marketing - Launch of new product
17 | Marketing - Launch of new product
18 | Marketing - Launch of new product
19 | Marketing - Launch of new product
20 | Marketing - Launch of new product
21 | Marketing - Launch of new product
22 | Marketing - Launch of new product
23 | Marketing - Launch of new product
24 | Marketing - Launch of new product
25 | Marketing - Launch of new product
26 | Marketing - Launch of new product
27 | Marketing - Launch of new product
28 | Marketing - Launch of new product
29 | Marketing - Launch of new product
30 | Marketing - Launch of new product
31 | Marketing - Launch of new product
32 | Marketing - Launch of new product
33 | Marketing - Launch of new product
34 | Marketing - Launch of new product
35 | Marketing - Launch of new product
36 | Marketing - Launch of new product
37 | Marketing - Launch of new product
38 | Marketing - Launch of new product
39 | Marketing - Launch of new product
40 | Marketing - Launch of new product
41 | Marketing - Launch of new product
42 | Marketing - Launch of new product
43 | Marketing - Launch of new product
44 | Marketing - Launch of new product
45 | Marketing - Launch of new product
46 | Marketing - Launch of new product
47 | Marketing - Launch of new product
48 | Marketing - Launch of new product
49 | Marketing - Launch of new product
50 | Marketing - Launch of new product
51 | Marketing - Launch of new product
52 | IT - CRM Implementation
53 | IT - CRM Implementation
54 | IT - CRM Implementation
55 | IT - CRM Implementation
56 | IT - CRM Implementation
57 | IT - CRM Implementation
58 | IT - CRM Implementation
59 | IT - CRM Implementation
60 | IT - CRM Implementation
61 | IT - CRM Implementation
62 | IT - CRM Implementation
63 | IT - CRM Implementation
64 | IT - CRM Implementation
65 | IT - CRM Implementation
66 | IT - CRM Implementation
67 | IT - CRM Implementation
68 | IT - CRM Implementation
69 | IT - CRM Implementation
70 | IT - CRM Implementation
71 | IT - CRM Implementation
72 | IT - CRM Implementation
73 | IT - CRM Implementation
74 | IT - CRM Implementation
75 | IT - CRM Implementation
76 | IT - CRM Implementation
77 | IT - CRM Implementation
78 | IT - CRM Implementation
79 | IT - CRM Implementation
80 | IT - CRM Implementation
81 | IT - CRM Implementation
82 | IT - CRM Implementation
83 | IT - CRM Implementation
84 | IT - CRM Implementation
85 | IT - CRM Implementation
86 | IT - CRM Implementation
87 | IT - CRM Implementation
88 | IT - CRM Implementation
89 | IT - CRM Implementation
90 | IT - CRM Implementation
91 | IT - CRM Implementation
92 | IT - CRM Implementation
93 | IT - CRM Implementation
94 | IT - CRM Implementation
95 | IT - CRM Implementation
96 | IT - CRM Implementation
97 | IT - CRM Implementation
98 | IT - CRM Implementation
99 | IT - CRM Implementation
100 | IT - CRM Implementation
101 | IT - CRM Implementation
102 | IT - CRM Implementation
103 | IT - CRM Implementation
104 | Marketing - Launch of new product

## Actual_Costs
Project_ID | Phase | Actual_Cost
1 | Phase 1 - Planning | 64000
2 | Phase 1 - Planning | 91000
3 | Phase 1 - Planning | 63000
4 | Phase 1 - Planning | 61500
5 | Phase 1 - Planning | 49500
6 | Phase 1 - Planning | 61500
7 | Phase 1 - Planning | 99000
8 | Phase 1 - Planning | 101000
9 | Phase 1 - Planning | 119000
10 | Phase 1 - Planning | 31000
11 | Phase 1 - Planning | 112000
12 | Phase 1 - Planning | 45500
13 | Phase 1 - Planning | 45500
14 | Phase 1 - Planning | 61500
15 | Phase 1 - Planning | 33666.6667
16 | Phase 1 - Planning | 43333.3333
17 | Phase 1 - Planning | 98000
18 | Phase 1 - Planning | 31666.6667
19 | Phase 1 - Planning | 101000
20 | Phase 1 - Planning | 61000
21 | Phase 1 - Planning | 51000
22 | Phase 1 - Planning | 54500
23 | Phase 1 - Planning | 122000
24 | Phase 1 - Planning | 51500
25 | Phase 1 - Planning | 38666.6667
26 | Phase 1 - Planning | 109000
27 | Phase 1 - Planning | 52000
28 | Phase 1 - Planning | 102000
29 | Phase 1 - Planning | 58500
30 | Phase 1 - Planning | 103000
31 | Phase 1 - Planning | 111000
32 | Phase 1 - Planning | 63500
33 | Phase 1 - Planning | 45000
34 | Phase 1 - Planning | 108000
35 | Phase 1 - Planning | 103000
36 | Phase 1 - Planning | 52500
37 | Phase 1 - Planning | 63000
38 | Phase 1 - Planning | 45500
39 | Phase 1 - Planning | 118000
40 | Phase 1 - Planning | 36000
41 | Phase 1 - Planning | 119000
42 | Phase 1 - Planning | 64000
43 | Phase 1 - Planning | 126000
44 | Phase 1 - Planning | 54000
45 | Phase 1 - Planning | 42333.3333
46 | Phase 1 - Planning | 65000
47 | Phase 1 - Planning | 30000
48 | Phase 1 - Planning | 110000
49 | Phase 1 - Planning | 57500
50 | Phase 1 - Planning | 64000
51 | Phase 1 - Planning | 116000
104 | Phase 1 - Planning | 48000
1 | Phase 2 - Initiation | 128000
2 | Phase 2 - Initiation | 182000
3 | Phase 2 - Initiation | 126000
4 | Phase 2 - Initiation | 123000
5 | Phase 2 - Initiation | 99000
6 | Phase 2 - Initiation | 123000
7 | Phase 2 - Initiation | 198000
8 | Phase 2 - Initiation | 202000
9 | Phase 2 - Initiation | 238000
10 | Phase 2 - Initiation | 62000
11 | Phase 2 - Initiation | 224000
12 | Phase 2 - Initiation | 91000
13 | Phase 2 - Initiation | 91000
14 | Phase 2 - Initiation | 123000
15 | Phase 2 - Initiation | 67333.3333
16 | Phase 2 - Initiation | 86666.6667
17 | Phase 2 - Initiation | 196000
18 | Phase 2 - Initiation | 63333.3333
19 | Phase 2 - Initiation | 202000
20 | Phase 2 - Initiation | 122000
21 | Phase 2 - Initiation | 102000
22 | Phase 2 - Initiation | 109000
23 | Phase 2 - Initiation | 244000
24 | Phase 2 - Initiation | 103000
25 | Phase 2 - Initiation | 77333.3333
26 | Phase 2 - Initiation | 218000
27 | Phase 2 - Initiation | 104000
28 | Phase 2 - Initiation | 204000
29 | Phase 2 - Initiation | 117000
30 | Phase 2 - Initiation | 206000
31 | Phase 2 - Initiation | 222000
32 | Phase 2 - Initiation | 127000
33 | Phase 2 - Initiation | 90000
34 | Phase 2 - Initiation | 216000
35 | Phase 2 - Initiation | 206000
36 | Phase 2 - Initiation | 105000
37 | Phase 2 - Initiation | 126000
38 | Phase 2 - Initiation | 91000
39 | Phase 2 - Initiation | 236000
40 | Phase 2 - Initiation | 72000
41 | Phase 2 - Initiation | 238000
42 | Phase 2 - Initiation | 128000
43 | Phase 2 - Initiation | 252000
44 | Phase 2 - Initiation | 108000
45 | Phase 2 - Initiation | 84666.6667
46 | Phase 2 - Initiation | 130000
47 | Phase 2 - Initiation | 60000
48 | Phase 2 - Initiation | 220000
49 | Phase 2 - Initiation | 115000
50 | Phase 2 - Initiation | 128000
51 | Phase 2 - Initiation | 232000
104 | Phase 2 - Initiation | 96000
1 | Phase 3 - Implementation | 192000
2 | Phase 3 - Implementation | 273000
3 | Phase 3 - Implementation | 189000
4 | Phase 3 - Implementation | 184500
5 | Phase 3 - Implementation | 148500
6 | Phase 3 - Implementation | 184500
7 | Phase 3 - Implementation | 297000
8 | Phase 3 - Implementation | 303000
9 | Phase 3 - Implementation | 357000
10 | Phase 3 - Implementation | 93000
11 | Phase 3 - Implementation | 336000
12 | Phase 3 - Implementation | 136500
13 | Phase 3 - Implementation | 136500
14 | Phase 3 - Implementation | 184500
15 | Phase 3 - Implementation | 101000
16 | Phase 3 - Implementation | 130000
17 | Phase 3 - Implementation | 294000
18 | Phase 3 - Implementation | 95000
19 | Phase 3 - Implementation | 303000
20 | Phase 3 - Implementation | 183000
21 | Phase 3 - Implementation | 153000
22 | Phase 3 - Implementation | 163500
23 | Phase 3 - Implementation | 366000
24 | Phase 3 - Implementation | 154500
25 | Phase 3 - Implementation | 116000
26 | Phase 3 - Implementation | 327000
27 | Phase 3 - Implementation | 156000
28 | Phase 3 - Implementation | 306000
29 | Phase 3 - Implementation | 175500
30 | Phase 3 - Implementation | 309000
31 | Phase 3 - Implementation | 333000
32 | Phase 3 - Implementation | 190500
33 | Phase 3 - Implementation | 135000
34 | Phase 3 - Implementation | 324000
35 | Phase 3 - Implementation | 309000
36 | Phase 3 - Implementation | 157500
37 | Phase 3 - Implementation | 189000
38 | Phase 3 - Implementation | 136500
39 | Phase 3 - Implementation | 354000
40 | Phase 3 - Implementation | 108000
41 | Phase 3 - Implementation | 357000
42 | Phase 3 - Implementation | 192000
43 | Phase 3 - Implementation | 378000
44 | Phase 3 - Implementation | 162000
45 | Phase 3 - Implementation | 127000
46 | Phase 3 - Implementation | 195000
47 | Phase 3 - Implementation | 90000
48 | Phase 3 - Implementation | 330000
49 | Phase 3 - Implementation | 172500
50 | Phase 3 - Implementation | 192000
51 | Phase 3 - Implementation | 348000
104 | Phase 3 - Implementation | 144000
1 | Phase 4 - Manufacturing | 576000
2 | Phase 4 - Manufacturing | 819000
3 | Phase 4 - Manufacturing | 567000
4 | Phase 4 - Manufacturing | 553500
5 | Phase 4 - Manufacturing | 445500
6 | Phase 4 - Manufacturing | 553500
7 | Phase 4 - Manufacturing | 891000
8 | Phase 4 - Manufacturing | 909000
9 | Phase 4 - Manufacturing | 1071000
10 | Phase 4 - Manufacturing | 279000
11 | Phase 4 - Manufacturing | 1008000
12 | Phase 4 - Manufacturing | 409500
13 | Phase 4 - Manufacturing | 409500
14 | Phase 4 - Manufacturing | 553500
15 | Phase 4 - Manufacturing | 303000
16 | Phase 4 - Manufacturing | 390000
17 | Phase 4 - Manufacturing | 882000
18 | Phase 4 - Manufacturing | 285000
19 | Phase 4 - Manufacturing | 909000
20 | Phase 4 - Manufacturing | 549000
21 | Phase 4 - Manufacturing | 459000
22 | Phase 4 - Manufacturing | 490500
23 | Phase 4 - Manufacturing | 1098000
24 | Phase 4 - Manufacturing | 463500
25 | Phase 4 - Manufacturing | 348000
26 | Phase 4 - Manufacturing | 981000
27 | Phase 4 - Manufacturing | 468000
28 | Phase 4 - Manufacturing | 918000
29 | Phase 4 - Manufacturing | 526500
30 | Phase 4 - Manufacturing | 927000
31 | Phase 4 - Manufacturing | 999000
32 | Phase 4 - Manufacturing | 571500
33 | Phase 4 - Manufacturing | 405000
34 | Phase 4 - Manufacturing | 972000
35 | Phase 4 - Manufacturing | 927000
36 | Phase 4 - Manufacturing | 472500
37 | Phase 4 - Manufacturing | 567000
38 | Phase 4 - Manufacturing | 409500
39 | Phase 4 - Manufacturing | 1062000
40 | Phase 4 - Manufacturing | 324000
41 | Phase 4 - Manufacturing | 1071000
42 | Phase 4 - Manufacturing | 576000
43 | Phase 4 - Manufacturing | 1134000
44 | Phase 4 - Manufacturing | 486000
45 | Phase 4 - Manufacturing | 381000
46 | Phase 4 - Manufacturing | 585000
47 | Phase 4 - Manufacturing | 270000
48 | Phase 4 - Manufacturing | 990000
49 | Phase 4 - Manufacturing | 517500
50 | Phase 4 - Manufacturing | 576000
51 | Phase 4 - Manufacturing | 1044000
104 | Phase 4 - Manufacturing | 432000
52 | Phase A - Initiation | 854
53 | Phase A - Initiation | 749
54 | Phase A - Initiation | 798
55 | Phase A - Initiation | 847
56 | Phase A - Initiation | 665
57 | Phase A - Initiation | 679
58 | Phase A - Initiation | 805
59 | Phase A - Initiation | 339.5
60 | Phase A - Initiation | 416.5
61 | Phase A - Initiation | 770
62 | Phase A - Initiation | 889
63 | Phase A - Initiation | 784
64 | Phase A - Initiation | 423.5
65 | Phase A - Initiation | 420
66 | Phase A - Initiation | 896
67 | Phase A - Initiation | 385
68 | Phase A - Initiation | 336
69 | Phase A - Initiation | 791
70 | Phase A - Initiation | 420
71 | Phase A - Initiation | 325.5
72 | Phase A - Initiation | 448
73 | Phase A - Initiation | 420
74 | Phase A - Initiation | 357
75 | Phase A - Initiation | 665
76 | Phase A - Initiation | 448
77 | Phase A - Initiation | 364
78 | Phase A - Initiation | 409.5
79 | Phase A - Initiation | 777
80 | Phase A - Initiation | 812
81 | Phase A - Initiation | 840
82 | Phase A - Initiation | 707
83 | Phase A - Initiation | 240.3333
84 | Phase A - Initiation | 212.3333
85 | Phase A - Initiation | 402.5
86 | Phase A - Initiation | 273
87 | Phase A - Initiation | 226.3333
88 | Phase A - Initiation | 296.3333
89 | Phase A - Initiation | 256.6667
90 | Phase A - Initiation | 259
91 | Phase A - Initiation | 221.6667
92 | Phase A - Initiation | 364
93 | Phase A - Initiation | 427
94 | Phase A - Initiation | 763
95 | Phase A - Initiation | 374.5
96 | Phase A - Initiation | 353.5
97 | Phase A - Initiation | 444.5
98 | Phase A - Initiation | 448
99 | Phase A - Initiation | 430.5
100 | Phase A - Initiation | 325.5
101 | Phase A - Initiation | 707
102 | Phase A - Initiation | 451.5
103 | Phase A - Initiation | 430.5
52 | Phase B - Preparation | 19642
53 | Phase B - Preparation | 17227
54 | Phase B - Preparation | 18354
55 | Phase B - Preparation | 19481
56 | Phase B - Preparation | 15295
57 | Phase B - Preparation | 15617
58 | Phase B - Preparation | 18515
59 | Phase B - Preparation | 2157975
60 | Phase B - Preparation | 2804819
61 | Phase B - Preparation | 17710
62 | Phase B - Preparation | 20447
63 | Phase B - Preparation | 18032
64 | Phase B - Preparation | 2863624
65 | Phase B - Preparation | 9660
66 | Phase B - Preparation | 20608
67 | Phase B - Preparation | 8855
68 | Phase B - Preparation | 7728
69 | Phase B - Preparation | 18193
70 | Phase B - Preparation | 9660
71 | Phase B - Preparation | 2040367
72 | Phase B - Preparation | 10304
73 | Phase B - Preparation | 9660
74 | Phase B - Preparation | 8211
75 | Phase B - Preparation | 15295
76 | Phase B - Preparation | 10304
77 | Phase B - Preparation | 8372
78 | Phase B - Preparation | 2746015
79 | Phase B - Preparation | 17871
80 | Phase B - Preparation | 18676
81 | Phase B - Preparation | 19320
82 | Phase B - Preparation | 16261
83 | Phase B - Preparation | 5527.6667
84 | Phase B - Preparation | 4883.6667
85 | Phase B - Preparation | 2687212
86 | Phase B - Preparation | 6279
87 | Phase B - Preparation | 5205.6667
88 | Phase B - Preparation | 6815.6667
89 | Phase B - Preparation | 5903.3333
90 | Phase B - Preparation | 5957
91 | Phase B - Preparation | 5098.3333
92 | Phase B - Preparation | 8372
93 | Phase B - Preparation | 9821
94 | Phase B - Preparation | 17549
95 | Phase B - Preparation | 2451995
96 | Phase B - Preparation | 2275583
97 | Phase B - Preparation | 10223.5
98 | Phase B - Preparation | 10304
99 | Phase B - Preparation | 2922427
100 | Phase B - Preparation | 2040367
101 | Phase B - Preparation | 16261
102 | Phase B - Preparation | 10384.5
103 | Phase B - Preparation | 2922427
52 | Phase C - Development | 25620
53 | Phase C - Development | 22470
54 | Phase C - Development | 23940
55 | Phase C - Development | 25410
56 | Phase C - Development | 19950
57 | Phase C - Development | 20370
58 | Phase C - Development | 24150
59 | Phase C - Development | 10185
60 | Phase C - Development | 12495
61 | Phase C - Development | 23100
62 | Phase C - Development | 26670
63 | Phase C - Development | 23520
64 | Phase C - Development | 12705
65 | Phase C - Development | 12600
66 | Phase C - Development | 26880
67 | Phase C - Development | 11550
68 | Phase C - Development | 10080
69 | Phase C - Development | 23730
70 | Phase C - Development | 12600
71 | Phase C - Development | 9765
72 | Phase C - Development | 13440
73 | Phase C - Development | 12600
74 | Phase C - Development | 10710
75 | Phase C - Development | 19950
76 | Phase C - Development | 13440
77 | Phase C - Development | 10920
78 | Phase C - Development | 12285
79 | Phase C - Development | 23310
80 | Phase C - Development | 24360
81 | Phase C - Development | 25200
82 | Phase C - Development | 21210
83 | Phase C - Development | 7210
84 | Phase C - Development | 6370
85 | Phase C - Development | 12075
86 | Phase C - Development | 8190
87 | Phase C - Development | 6790
88 | Phase C - Development | 8890
89 | Phase C - Development | 7700
90 | Phase C - Development | 7770
91 | Phase C - Development | 6650
92 | Phase C - Development | 10920
93 | Phase C - Development | 12810
94 | Phase C - Development | 22890
95 | Phase C - Development | 11235
96 | Phase C - Development | 10605
97 | Phase C - Development | 13335
98 | Phase C - Development | 13440
99 | Phase C - Development | 12915
100 | Phase C - Development | 9765
101 | Phase C - Development | 21210
102 | Phase C - Development | 13545
103 | Phase C - Development | 12915
52 | Phase D - Testing | 19624
53 | Phase D - Testing | 24265
54 | Phase D - Testing | 17034
55 | Phase D - Testing | 18172
56 | Phase D - Testing | 17889
57 | Phase D - Testing | 16395
58 | Phase D - Testing | 18321
59 | Phase D - Testing | 13690
60 | Phase D - Testing | 18587
61 | Phase D - Testing | 20589
62 | Phase D - Testing | 19055
63 | Phase D - Testing | 25297
64 | Phase D - Testing | 18418
65 | Phase D - Testing | 15857
66 | Phase D - Testing | 27104
67 | Phase D - Testing | 17764
68 | Phase D - Testing | 19083
69 | Phase D - Testing | 21915
70 | Phase D - Testing | 16694
71 | Phase D - Testing | 15109
72 | Phase D - Testing | 14801
73 | Phase D - Testing | 21345
74 | Phase D - Testing | 13178
75 | Phase D - Testing | 17625
76 | Phase D - Testing | 14567
77 | Phase D - Testing | 16378
78 | Phase D - Testing | 22202
79 | Phase D - Testing | 23732
80 | Phase D - Testing | 25458
81 | Phase D - Testing | 17441
82 | Phase D - Testing | 23587
83 | Phase D - Testing | 19613.6667
84 | Phase D - Testing | 13387.6667
85 | Phase D - Testing | 20861
86 | Phase D - Testing | 19936
87 | Phase D - Testing | 19877.6667
88 | Phase D - Testing | 18652.6667
89 | Phase D - Testing | 15385.3333
90 | Phase D - Testing | 13370
91 | Phase D - Testing | 18990.3333
92 | Phase D - Testing | 14576
93 | Phase D - Testing | 21164
94 | Phase D - Testing | 17640
95 | Phase D - Testing | 20024
96 | Phase D - Testing | 14732
97 | Phase D - Testing | 14013
98 | Phase D - Testing | 19997
99 | Phase D - Testing | 16483
100 | Phase D - Testing | 19201
101 | Phase D - Testing | 19250
102 | Phase D - Testing | 20048
103 | Phase D - Testing | 19808
52 | Phase E - Deployment | 0
53 | Phase E - Deployment | 0
54 | Phase E - Deployment | 0
55 | Phase E - Deployment | 0
56 | Phase E - Deployment | 0
57 | Phase E - Deployment | 0
58 | Phase E - Deployment | 0
59 | Phase E - Deployment | 0
60 | Phase E - Deployment | 0
61 | Phase E - Deployment | 0
62 | Phase E - Deployment | 0
63 | Phase E - Deployment | 0
64 | Phase E - Deployment | 0
65 | Phase E - Deployment | 0
66 | Phase E - Deployment | 0
67 | Phase E - Deployment | 0
68 | Phase E - Deployment | 0
69 | Phase E - Deployment | 0
70 | Phase E - Deployment | 0
71 | Phase E - Deployment | 0
72 | Phase E - Deployment | 0
73 | Phase E - Deployment | 0
74 | Phase E - Deployment | 0
75 | Phase E - Deployment | 0
76 | Phase E - Deployment | 0
77 | Phase E - Deployment | 0
78 | Phase E - Deployment | 0
79 | Phase E - Deployment | 0
80 | Phase E - Deployment | 0
81 | Phase E - Deployment | 0
82 | Phase E - Deployment | 0
83 | Phase E - Deployment | 0
84 | Phase E - Deployment | 0
85 | Phase E - Deployment | 0
86 | Phase E - Deployment | 0
87 | Phase E - Deployment | 0
88 | Phase E - Deployment | 0
89 | Phase E - Deployment | 0
90 | Phase E - Deployment | 0
91 | Phase E - Deployment | 0
92 | Phase E - Deployment | 0
93 | Phase E - Deployment | 0
94 | Phase E - Deployment | 0
95 | Phase E - Deployment | 0
96 | Phase E - Deployment | 0
97 | Phase E - Deployment | 0
98 | Phase E - Deployment | 0
99 | Phase E - Deployment | 0
100 | Phase E - Deployment | 0
101 | Phase E - Deployment | 0
102 | Phase E - Deployment | 0
103 | Phase E - Deployment | 0
52 | Phase F - Post-deployment | 3416
53 | Phase F - Post-deployment | 2996
54 | Phase F - Post-deployment | 3192
55 | Phase F - Post-deployment | 3388
56 | Phase F - Post-deployment | 2660
57 | Phase F - Post-deployment | 2716
58 | Phase F - Post-deployment | 3220
59 | Phase F - Post-deployment | 1358
60 | Phase F - Post-deployment | 1666
61 | Phase F - Post-deployment | 3080
62 | Phase F - Post-deployment | 3556
63 | Phase F - Post-deployment | 3136
64 | Phase F - Post-deployment | 1694
65 | Phase F - Post-deployment | 1680
66 | Phase F - Post-deployment | 3584
67 | Phase F - Post-deployment | 1540
68 | Phase F - Post-deployment | 1344
69 | Phase F - Post-deployment | 3164
70 | Phase F - Post-deployment | 1680
71 | Phase F - Post-deployment | 1302
72 | Phase F - Post-deployment | 1792
73 | Phase F - Post-deployment | 1680
74 | Phase F - Post-deployment | 1428
75 | Phase F - Post-deployment | 2660
76 | Phase F - Post-deployment | 1792
77 | Phase F - Post-deployment | 1456
78 | Phase F - Post-deployment | 1638
79 | Phase F - Post-deployment | 3108
80 | Phase F - Post-deployment | 3248
81 | Phase F - Post-deployment | 3360
82 | Phase F - Post-deployment | 2828
83 | Phase F - Post-deployment | 961.3333
84 | Phase F - Post-deployment | 849.3333
85 | Phase F - Post-deployment | 1610
86 | Phase F - Post-deployment | 1092
87 | Phase F - Post-deployment | 905.3333
88 | Phase F - Post-deployment | 1185.3333
89 | Phase F - Post-deployment | 1026.6667
90 | Phase F - Post-deployment | 1036
91 | Phase F - Post-deployment | 886.6667
92 | Phase F - Post-deployment | 1456
93 | Phase F - Post-deployment | 1708
94 | Phase F - Post-deployment | 3052
95 | Phase F - Post-deployment | 1498
96 | Phase F - Post-deployment | 1414
97 | Phase F - Post-deployment | 1778
98 | Phase F - Post-deployment | 1792
99 | Phase F - Post-deployment | 1722
100 | Phase F - Post-deployment | 1302
101 | Phase F - Post-deployment | 2828
102 | Phase F - Post-deployment | 1806
103 | Phase F - Post-deployment | 1722

## Actual_Duration
Project_ID | Phase | Actual_Duration
1 | Phase 1 - Planning | 15
1 | Phase 2 - Initiation | 76
1 | Phase 3 - Implementation | 176
1 | Phase 4 - Manufacturing | 64
2 | Phase 1 - Planning | 61
2 | Phase 2 - Initiation | 66
2 | Phase 3 - Implementation | 73
2 | Phase 4 - Manufacturing | 148
3 | Phase 1 - Planning | 22
3 | Phase 2 - Initiation | 34
3 | Phase 3 - Implementation | 178
3 | Phase 4 - Manufacturing | 127
4 | Phase 1 - Planning | 172
4 | Phase 2 - Initiation | 46
4 | Phase 3 - Implementation | 147
4 | Phase 4 - Manufacturing | 105
5 | Phase 1 - Planning | 25
5 | Phase 2 - Initiation | 20
5 | Phase 3 - Implementation | 62
5 | Phase 4 - Manufacturing | 52
6 | Phase 1 - Planning | 57
6 | Phase 2 - Initiation | 20
6 | Phase 3 - Implementation | 89
6 | Phase 4 - Manufacturing | 58
7 | Phase 1 - Planning | 51
7 | Phase 2 - Initiation | 59
7 | Phase 3 - Implementation | 143
7 | Phase 4 - Manufacturing | 120
8 | Phase 1 - Planning | 106
8 | Phase 2 - Initiation | 68
8 | Phase 3 - Implementation | 62
8 | Phase 4 - Manufacturing | 135
9 | Phase 1 - Planning | 32
9 | Phase 2 - Initiation | 52
9 | Phase 3 - Implementation | 44
9 | Phase 4 - Manufacturing | 73
10 | Phase 1 - Planning | 132
10 | Phase 2 - Initiation | 164
10 | Phase 3 - Implementation | 131
10 | Phase 4 - Manufacturing | 73
11 | Phase 1 - Planning | 107
11 | Phase 2 - Initiation | 20
11 | Phase 3 - Implementation | 168
11 | Phase 4 - Manufacturing | 156
12 | Phase 1 - Planning | 86
12 | Phase 2 - Initiation | 153
12 | Phase 3 - Implementation | 144
12 | Phase 4 - Manufacturing | 104
13 | Phase 1 - Planning | 106
13 | Phase 2 - Initiation | 97
13 | Phase 3 - Implementation | 139
13 | Phase 4 - Manufacturing | 153
14 | Phase 1 - Planning | 15
14 | Phase 2 - Initiation | 4
14 | Phase 3 - Implementation | 145
14 | Phase 4 - Manufacturing | 55
15 | Phase 1 - Planning | 18
15 | Phase 2 - Initiation | 171
15 | Phase 3 - Implementation | 81
15 | Phase 4 - Manufacturing | 71
16 | Phase 1 - Planning | 103
16 | Phase 2 - Initiation | 115
16 | Phase 3 - Implementation | 10
16 | Phase 4 - Manufacturing | 57
17 | Phase 1 - Planning | 97
17 | Phase 2 - Initiation | 67
17 | Phase 3 - Implementation | 147
17 | Phase 4 - Manufacturing | 180
18 | Phase 1 - Planning | 64
18 | Phase 2 - Initiation | 65
18 | Phase 3 - Implementation | 41
18 | Phase 4 - Manufacturing | 100
19 | Phase 1 - Planning | 19
19 | Phase 2 - Initiation | 155
19 | Phase 3 - Implementation | 110
19 | Phase 4 - Manufacturing | 144
20 | Phase 1 - Planning | 21
20 | Phase 2 - Initiation | 84
20 | Phase 3 - Implementation | 99
20 | Phase 4 - Manufacturing | 12
21 | Phase 1 - Planning | 54
21 | Phase 2 - Initiation | 170
21 | Phase 3 - Implementation | 106
21 | Phase 4 - Manufacturing | 45
22 | Phase 1 - Planning | 30
22 | Phase 2 - Initiation | 125
22 | Phase 3 - Implementation | 54
22 | Phase 4 - Manufacturing | 123
23 | Phase 1 - Planning | 57
23 | Phase 2 - Initiation | 79
23 | Phase 3 - Implementation | 135
23 | Phase 4 - Manufacturing | 34
24 | Phase 1 - Planning | 49
24 | Phase 2 - Initiation | 132
24 | Phase 3 - Implementation | 54
24 | Phase 4 - Manufacturing | 165
25 | Phase 1 - Planning | 30
25 | Phase 2 - Initiation | 8
25 | Phase 3 - Implementation | 63
25 | Phase 4 - Manufacturing | 73
26 | Phase 1 - Planning | 148
26 | Phase 2 - Initiation | 82
26 | Phase 3 - Implementation | 12
26 | Phase 4 - Manufacturing | 121
27 | Phase 1 - Planning | 114
27 | Phase 2 - Initiation | 151
27 | Phase 3 - Implementation | 28
27 | Phase 4 - Manufacturing | 168
28 | Phase 1 - Planning | 135
28 | Phase 2 - Initiation | 51
28 | Phase 3 - Implementation | 28
28 | Phase 4 - Manufacturing | 32
29 | Phase 1 - Planning | 140
29 | Phase 2 - Initiation | 43
29 | Phase 3 - Implementation | 116
29 | Phase 4 - Manufacturing | 33
30 | Phase 1 - Planning | 35
30 | Phase 2 - Initiation | 18
30 | Phase 3 - Implementation | 30
30 | Phase 4 - Manufacturing | 4
31 | Phase 1 - Planning | 62
31 | Phase 2 - Initiation | 150
31 | Phase 3 - Implementation | 54
31 | Phase 4 - Manufacturing | 49
32 | Phase 1 - Planning | 9
32 | Phase 2 - Initiation | 25
32 | Phase 3 - Implementation | 108
32 | Phase 4 - Manufacturing | 21
33 | Phase 1 - Planning | 65
33 | Phase 2 - Initiation | 12
33 | Phase 3 - Implementation | 110
33 | Phase 4 - Manufacturing | 82
34 | Phase 1 - Planning | 38
34 | Phase 2 - Initiation | 3
34 | Phase 3 - Implementation | 132
34 | Phase 4 - Manufacturing | 39
35 | Phase 1 - Planning | 30
35 | Phase 2 - Initiation | 96
35 | Phase 3 - Implementation | 77
35 | Phase 4 - Manufacturing | 22
36 | Phase 1 - Planning | 138
36 | Phase 2 - Initiation | 157
36 | Phase 3 - Implementation | 144
36 | Phase 4 - Manufacturing | 74
37 | Phase 1 - Planning | 128
37 | Phase 2 - Initiation | 75
37 | Phase 3 - Implementation | 92
37 | Phase 4 - Manufacturing | 28
38 | Phase 1 - Planning | 38
38 | Phase 2 - Initiation | 84
38 | Phase 3 - Implementation | 135
38 | Phase 4 - Manufacturing | 74
39 | Phase 1 - Planning | 160
39 | Phase 2 - Initiation | 148
39 | Phase 3 - Implementation | 121
39 | Phase 4 - Manufacturing | 172
40 | Phase 1 - Planning | 21
40 | Phase 2 - Initiation | 121
40 | Phase 3 - Implementation | 90
40 | Phase 4 - Manufacturing | 160
41 | Phase 1 - Planning | 84
41 | Phase 2 - Initiation | 21
41 | Phase 3 - Implementation | 4
41 | Phase 4 - Manufacturing | 48
42 | Phase 1 - Planning | 93
42 | Phase 2 - Initiation | 86
42 | Phase 3 - Implementation | 63
42 | Phase 4 - Manufacturing | 18
43 | Phase 1 - Planning | 83
43 | Phase 2 - Initiation | 92
43 | Phase 3 - Implementation | 129
43 | Phase 4 - Manufacturing | 50
44 | Phase 1 - Planning | 39
44 | Phase 2 - Initiation | 12
44 | Phase 3 - Implementation | 166
44 | Phase 4 - Manufacturing | 116
45 | Phase 1 - Planning | 154
45 | Phase 2 - Initiation | 60
45 | Phase 3 - Implementation | 51
45 | Phase 4 - Manufacturing | 56
46 | Phase 1 - Planning | 129
46 | Phase 2 - Initiation | 176
46 | Phase 3 - Implementation | 106
46 | Phase 4 - Manufacturing | 90
47 | Phase 1 - Planning | 40
47 | Phase 2 - Initiation | 180
47 | Phase 3 - Implementation | 87
47 | Phase 4 - Manufacturing | 126
48 | Phase 1 - Planning | 27
48 | Phase 2 - Initiation | 90
48 | Phase 3 - Implementation | 19
48 | Phase 4 - Manufacturing | 33
49 | Phase 1 - Planning | 172
49 | Phase 2 - Initiation | 41
49 | Phase 3 - Implementation | 70
49 | Phase 4 - Manufacturing | 39
50 | Phase 1 - Planning | 62
50 | Phase 2 - Initiation | 56
50 | Phase 3 - Implementation | 40
50 | Phase 4 - Manufacturing | 18
51 | Phase 1 - Planning | 108
51 | Phase 2 - Initiation | 43
51 | Phase 3 - Implementation | 158
51 | Phase 4 - Manufacturing | 133
52 | Phase E - Deployment | 114
52 | Phase C - Development | 137
52 | Phase A - Initiation | 109
52 | Phase F - Post-deployment | 86
52 | Phase B - Preparation | 36
52 | Phase D - Testing | 86
53 | Phase E - Deployment | 128
53 | Phase C - Development | 80
53 | Phase A - Initiation | 44
53 | Phase F - Post-deployment | 106
53 | Phase B - Preparation | 127
53 | Phase D - Testing | 46
54 | Phase E - Deployment | 79
54 | Phase C - Development | 69
54 | Phase A - Initiation | 28
54 | Phase F - Post-deployment | 157
54 | Phase B - Preparation | 152
54 | Phase D - Testing | 153
55 | Phase E - Deployment | 89
55 | Phase C - Development | 31
55 | Phase A - Initiation | 44
55 | Phase F - Post-deployment | 125
55 | Phase B - Preparation | 139
55 | Phase D - Testing | 64
56 | Phase E - Deployment | 174
56 | Phase C - Development | 116
56 | Phase A - Initiation | 8
56 | Phase F - Post-deployment | 53
56 | Phase B - Preparation | 102
56 | Phase D - Testing | 93
57 | Phase E - Deployment | 56
57 | Phase C - Development | 33
57 | Phase A - Initiation | 165
57 | Phase F - Post-deployment | 88
57 | Phase B - Preparation | 166
57 | Phase D - Testing | 129
58 | Phase E - Deployment | 136
58 | Phase C - Development | 147
58 | Phase A - Initiation | 75
58 | Phase F - Post-deployment | 159
58 | Phase B - Preparation | 103
58 | Phase D - Testing | 77
59 | Phase E - Deployment | 124
59 | Phase C - Development | 138
59 | Phase A - Initiation | 83
59 | Phase F - Post-deployment | 151
59 | Phase B - Preparation | 32
59 | Phase D - Testing | 129
60 | Phase E - Deployment | 28
60 | Phase C - Development | 159
60 | Phase A - Initiation | 85
60 | Phase F - Post-deployment | 146
60 | Phase B - Preparation | 158
60 | Phase D - Testing | 175
61 | Phase E - Deployment | 67
61 | Phase C - Development | 4
61 | Phase A - Initiation | 30
61 | Phase F - Post-deployment | 99
61 | Phase B - Preparation | 149
61 | Phase D - Testing | 6
62 | Phase E - Deployment | 80
62 | Phase C - Development | 77
62 | Phase A - Initiation | 35
62 | Phase F - Post-deployment | 36
62 | Phase B - Preparation | 3
62 | Phase D - Testing | 57
63 | Phase E - Deployment | 38
63 | Phase C - Development | 143
63 | Phase A - Initiation | 28
63 | Phase F - Post-deployment | 161
63 | Phase B - Preparation | 123
63 | Phase D - Testing | 29
64 | Phase E - Deployment | 165
64 | Phase C - Development | 24
64 | Phase A - Initiation | 71
64 | Phase F - Post-deployment | 31
64 | Phase B - Preparation | 127
64 | Phase D - Testing | 119
65 | Phase E - Deployment | 153
65 | Phase C - Development | 83
65 | Phase A - Initiation | 107
65 | Phase F - Post-deployment | 161
65 | Phase B - Preparation | 123
65 | Phase D - Testing | 56
66 | Phase E - Deployment | 140
66 | Phase C - Development | 160
66 | Phase A - Initiation | 131
66 | Phase F - Post-deployment | 93
66 | Phase B - Preparation | 57
66 | Phase D - Testing | 148
67 | Phase E - Deployment | 48
67 | Phase C - Development | 63
67 | Phase A - Initiation | 7
67 | Phase F - Post-deployment | 89
67 | Phase B - Preparation | 35
67 | Phase D - Testing | 96
68 | Phase E - Deployment | 120
68 | Phase C - Development | 54
68 | Phase A - Initiation | 159
68 | Phase F - Post-deployment | 71
68 | Phase B - Preparation | 18
68 | Phase D - Testing | 66
69 | Phase E - Deployment | 171
69 | Phase C - Development | 158
69 | Phase A - Initiation | 81
69 | Phase F - Post-deployment | 110
69 | Phase B - Preparation | 134
69 | Phase D - Testing | 80
70 | Phase E - Deployment | 171
70 | Phase C - Development | 42
70 | Phase A - Initiation | 98
70 | Phase F - Post-deployment | 108
70 | Phase B - Preparation | 130
70 | Phase D - Testing | 115
71 | Phase E - Deployment | 124
71 | Phase C - Development | 40
71 | Phase A - Initiation | 79
71 | Phase F - Post-deployment | 41
71 | Phase B - Preparation | 173
71 | Phase D - Testing | 44
72 | Phase E - Deployment | 65
72 | Phase C - Development | 80
72 | Phase A - Initiation | 15
72 | Phase F - Post-deployment | 53
72 | Phase B - Preparation | 6
72 | Phase D - Testing | 64
73 | Phase E - Deployment | 19
73 | Phase C - Development | 111
73 | Phase A - Initiation | 86
73 | Phase F - Post-deployment | 102
73 | Phase B - Preparation | 173
73 | Phase D - Testing | 73
74 | Phase E - Deployment | 60
74 | Phase C - Development | 33
74 | Phase A - Initiation | 129
74 | Phase F - Post-deployment | 113
74 | Phase B - Preparation | 58
74 | Phase D - Testing | 117
75 | Phase E - Deployment | 77
75 | Phase C - Development | 124
75 | Phase A - Initiation | 84
75 | Phase F - Post-deployment | 97
75 | Phase B - Preparation | 56
75 | Phase D - Testing | 73
76 | Phase E - Deployment | 128
76 | Phase C - Development | 138
76 | Phase A - Initiation | 175
76 | Phase F - Post-deployment | 13
76 | Phase B - Preparation | 120
76 | Phase D - Testing | 125
77 | Phase E - Deployment | 102
77 | Phase C - Development | 132
77 | Phase A - Initiation | 117
77 | Phase F - Post-deployment | 159
77 | Phase B - Preparation | 29
77 | Phase D - Testing | 161
78 | Phase E - Deployment | 178
78 | Phase C - Development | 27
78 | Phase A - Initiation | 140
78 | Phase F - Post-deployment | 29
78 | Phase B - Preparation | 128
78 | Phase D - Testing | 39
79 | Phase E - Deployment | 67
79 | Phase C - Development | 72
79 | Phase A - Initiation | 109
79 | Phase F - Post-deployment | 108
79 | Phase B - Preparation | 156
79 | Phase D - Testing | 49
80 | Phase E - Deployment | 70
80 | Phase C - Development | 141
80 | Phase A - Initiation | 38
80 | Phase F - Post-deployment | 83
80 | Phase B - Preparation | 33
80 | Phase D - Testing | 171
81 | Phase E - Deployment | 12
81 | Phase C - Development | 153
81 | Phase A - Initiation | 138
81 | Phase F - Post-deployment | 121
81 | Phase B - Preparation | 50
81 | Phase D - Testing | 163
82 | Phase E - Deployment | 37
82 | Phase C - Development | 134
82 | Phase A - Initiation | 65
82 | Phase F - Post-deployment | 104
82 | Phase B - Preparation | 13
82 | Phase D - Testing | 102
83 | Phase E - Deployment | 156
83 | Phase C - Development | 40
83 | Phase A - Initiation | 129
83 | Phase F - Post-deployment | 110
83 | Phase B - Preparation | 10
83 | Phase D - Testing | 121
84 | Phase E - Deployment | 122
84 | Phase C - Development | 138
84 | Phase A - Initiation | 63
84 | Phase F - Post-deployment | 135
84 | Phase B - Preparation | 152
84 | Phase D - Testing | 179
85 | Phase E - Deployment | 135
85 | Phase C - Development | 118
85 | Phase A - Initiation | 82
85 | Phase F - Post-deployment | 172
85 | Phase B - Preparation | 135
85 | Phase D - Testing | 146
86 | Phase E - Deployment | 154
86 | Phase C - Development | 125
86 | Phase A - Initiation | 75
86 | Phase F - Post-deployment | 132
86 | Phase B - Preparation | 128
86 | Phase D - Testing | 53
87 | Phase E - Deployment | 178
87 | Phase C - Development | 116
87 | Phase A - Initiation | 83
87 | Phase F - Post-deployment | 152
87 | Phase B - Preparation | 119
87 | Phase D - Testing | 141
88 | Phase E - Deployment | 3
88 | Phase C - Development | 59
88 | Phase A - Initiation | 162
88 | Phase F - Post-deployment | 11
88 | Phase B - Preparation | 103
88 | Phase D - Testing | 146
89 | Phase E - Deployment | 95
89 | Phase C - Development | 23
89 | Phase A - Initiation | 174
89 | Phase F - Post-deployment | 97
89 | Phase B - Preparation | 170
89 | Phase D - Testing | 93
90 | Phase E - Deployment | 51
90 | Phase C - Development | 95
90 | Phase A - Initiation | 86
90 | Phase F - Post-deployment | 31
90 | Phase B - Preparation | 176
90 | Phase D - Testing | 155
91 | Phase E - Deployment | 18
91 | Phase C - Development | 92
91 | Phase A - Initiation | 46
91 | Phase F - Post-deployment | 92
91 | Phase B - Preparation | 124
91 | Phase D - Testing | 78
92 | Phase E - Deployment | 39
92 | Phase C - Development | 164
92 | Phase A - Initiation | 96
92 | Phase F - Post-deployment | 125
92 | Phase B - Preparation | 133
92 | Phase D - Testing | 113
93 | Phase E - Deployment | 132
93 | Phase C - Development | 60
93 | Phase A - Initiation | 125
93 | Phase F - Post-deployment | 87
93 | Phase B - Preparation | 104
93 | Phase D - Testing | 160
94 | Phase E - Deployment | 10
94 | Phase C - Development | 174
94 | Phase A - Initiation | 67
94 | Phase F - Post-deployment | 143
94 | Phase B - Preparation | 45
94 | Phase D - Testing | 30
95 | Phase E - Deployment | 164
95 | Phase C - Development | 45
95 | Phase A - Initiation | 91
95 | Phase F - Post-deployment | 102
95 | Phase B - Preparation | 127
95 | Phase D - Testing | 85
96 | Phase E - Deployment | 24
96 | Phase C - Development | 114
96 | Phase A - Initiation | 73
96 | Phase F - Post-deployment | 178
96 | Phase B - Preparation | 68
96 | Phase D - Testing | 100
97 | Phase E - Deployment | 142
97 | Phase C - Development | 76
97 | Phase A - Initiation | 60
97 | Phase F - Post-deployment | 23
97 | Phase B - Preparation | 6
97 | Phase D - Testing | 80
98 | Phase E - Deployment | 140
98 | Phase C - Development | 100
98 | Phase A - Initiation | 172
98 | Phase F - Post-deployment | 44
98 | Phase B - Preparation | 37
98 | Phase D - Testing | 50
99 | Phase E - Deployment | 7
99 | Phase C - Development | 54
99 | Phase A - Initiation | 83
99 | Phase F - Post-deployment | 85
99 | Phase B - Preparation | 16
99 | Phase D - Testing | 36
100 | Phase E - Deployment | 9
100 | Phase C - Development | 167
100 | Phase A - Initiation | 32
100 | Phase F - Post-deployment | 122
100 | Phase B - Preparation | 15
100 | Phase D - Testing | 150
101 | Phase E - Deployment | 65
101 | Phase C - Development | 175
101 | Phase A - Initiation | 69
101 | Phase F - Post-deployment | 99
101 | Phase B - Preparation | 71
101 | Phase D - Testing | 86
102 | Phase E - Deployment | 150
102 | Phase C - Development | 152
102 | Phase A - Initiation | 65
102 | Phase F - Post-deployment | 82
102 | Phase B - Preparation | 9
102 | Phase D - Testing | 31
103 | Phase E - Deployment | 75
103 | Phase C - Development | 85
103 | Phase A - Initiation | 116
103 | Phase F - Post-deployment | 171
103 | Phase B - Preparation | 41
103 | Phase D - Testing | 31
104 | Phase 1 - Planning | 26
104 | Phase 2 - Initiation | 16
104 | Phase 3 - Implementation | 168
104 | Phase 4 - Manufacturing | 140

## Deliverables_status
Project_ID | Phase | Var_Deliverables
1 | Phase 1 - Planning | -0.05
1 | Phase 2 - Initiation | -0.08
1 | Phase 3 - Implementation | -0.05
1 | Phase 4 - Manufacturing | -0.01
2 | Phase 1 - Planning | -0.02
2 | Phase 2 - Initiation | -0.13
2 | Phase 3 - Implementation | -0.14
2 | Phase 4 - Manufacturing | -0.06
3 | Phase 1 - Planning | 0
3 | Phase 2 - Initiation | -0.12
3 | Phase 3 - Implementation | -0.13
3 | Phase 4 - Manufacturing | -0.06
4 | Phase 1 - Planning | 0
4 | Phase 2 - Initiation | -0.04
4 | Phase 3 - Implementation | -0.09
4 | Phase 4 - Manufacturing | -0.02
5 | Phase 1 - Planning | -0.01
5 | Phase 2 - Initiation | -0.11
5 | Phase 3 - Implementation | -0.01
5 | Phase 4 - Manufacturing | -0.03
6 | Phase 1 - Planning | -0.06
6 | Phase 2 - Initiation | -0.14
6 | Phase 3 - Implementation | -0.06
6 | Phase 4 - Manufacturing | -0.12
7 | Phase 1 - Planning | -0.07
7 | Phase 2 - Initiation | -0.06
7 | Phase 3 - Implementation | 0
7 | Phase 4 - Manufacturing | -0.12
8 | Phase 1 - Planning | -0.1
8 | Phase 2 - Initiation | -0.12
8 | Phase 3 - Implementation | -0.05
8 | Phase 4 - Manufacturing | -0.05
9 | Phase 1 - Planning | -0.14
9 | Phase 2 - Initiation | -0.03
9 | Phase 3 - Implementation | -0.11
9 | Phase 4 - Manufacturing | -0.01
10 | Phase 1 - Planning | -0.04
10 | Phase 2 - Initiation | -0.05
10 | Phase 3 - Implementation | -0.07
10 | Phase 4 - Manufacturing | -0.12
11 | Phase 1 - Planning | -0.11
11 | Phase 2 - Initiation | -0.08
11 | Phase 3 - Implementation | 0
11 | Phase 4 - Manufacturing | -0.14
12 | Phase 1 - Planning | -0.07
12 | Phase 2 - Initiation | -0.14
12 | Phase 3 - Implementation | -0.11
12 | Phase 4 - Manufacturing | -0.13
13 | Phase 1 - Planning | -0.14
13 | Phase 2 - Initiation | -0.05
13 | Phase 3 - Implementation | -0.13
13 | Phase 4 - Manufacturing | -0.03
14 | Phase 1 - Planning | -0.05
14 | Phase 2 - Initiation | -0.08
14 | Phase 3 - Implementation | -0.05
14 | Phase 4 - Manufacturing | -0.01
15 | Phase 1 - Planning | -0.02
15 | Phase 2 - Initiation | -0.13
15 | Phase 3 - Implementation | -0.14
15 | Phase 4 - Manufacturing | -0.06
16 | Phase 1 - Planning | 0
16 | Phase 2 - Initiation | -0.12
16 | Phase 3 - Implementation | -0.13
16 | Phase 4 - Manufacturing | -0.06
17 | Phase 1 - Planning | 0
17 | Phase 2 - Initiation | -0.04
17 | Phase 3 - Implementation | -0.09
17 | Phase 4 - Manufacturing | -0.02
18 | Phase 1 - Planning | -0.01
18 | Phase 2 - Initiation | -0.11
18 | Phase 3 - Implementation | -0.01
18 | Phase 4 - Manufacturing | -0.03
19 | Phase 1 - Planning | -0.06
19 | Phase 2 - Initiation | -0.14
19 | Phase 3 - Implementation | -0.06
19 | Phase 4 - Manufacturing | -0.12
20 | Phase 1 - Planning | -0.07
20 | Phase 2 - Initiation | -0.06
20 | Phase 3 - Implementation | 0
20 | Phase 4 - Manufacturing | -0.12
21 | Phase 1 - Planning | -0.1
21 | Phase 2 - Initiation | -0.12
21 | Phase 3 - Implementation | -0.05
21 | Phase 4 - Manufacturing | -0.05
22 | Phase 1 - Planning | -0.14
22 | Phase 2 - Initiation | -0.03
22 | Phase 3 - Implementation | -0.11
22 | Phase 4 - Manufacturing | -0.01
23 | Phase 1 - Planning | -0.04
23 | Phase 2 - Initiation | -0.05
23 | Phase 3 - Implementation | -0.07
23 | Phase 4 - Manufacturing | -0.12
24 | Phase 1 - Planning | -0.11
24 | Phase 2 - Initiation | -0.08
24 | Phase 3 - Implementation | 0
24 | Phase 4 - Manufacturing | -0.14
25 | Phase 1 - Planning | -0.07
25 | Phase 2 - Initiation | -0.14
25 | Phase 3 - Implementation | -0.11
25 | Phase 4 - Manufacturing | -0.13
26 | Phase 1 - Planning | -0.14
26 | Phase 2 - Initiation | -0.05
26 | Phase 3 - Implementation | -0.13
26 | Phase 4 - Manufacturing | -0.03
27 | Phase 1 - Planning | -0.05
27 | Phase 2 - Initiation | -0.08
27 | Phase 3 - Implementation | -0.05
27 | Phase 4 - Manufacturing | -0.01
28 | Phase 1 - Planning | -0.02
28 | Phase 2 - Initiation | -0.13
28 | Phase 3 - Implementation | -0.14
28 | Phase 4 - Manufacturing | -0.06
29 | Phase 1 - Planning | 0
29 | Phase 2 - Initiation | -0.12
29 | Phase 3 - Implementation | -0.13
29 | Phase 4 - Manufacturing | -0.06
30 | Phase 1 - Planning | 0
30 | Phase 2 - Initiation | -0.04
30 | Phase 3 - Implementation | -0.09
30 | Phase 4 - Manufacturing | -0.02
31 | Phase 1 - Planning | -0.01
31 | Phase 2 - Initiation | -0.11
31 | Phase 3 - Implementation | -0.01
31 | Phase 4 - Manufacturing | -0.03
32 | Phase 1 - Planning | -0.06
32 | Phase 2 - Initiation | -0.14
32 | Phase 3 - Implementation | -0.06
32 | Phase 4 - Manufacturing | -0.12
33 | Phase 1 - Planning | -0.07
33 | Phase 2 - Initiation | -0.06
33 | Phase 3 - Implementation | 0
33 | Phase 4 - Manufacturing | -0.12
34 | Phase 1 - Planning | -0.1
34 | Phase 2 - Initiation | -0.12
34 | Phase 3 - Implementation | -0.05
34 | Phase 4 - Manufacturing | -0.05
35 | Phase 1 - Planning | -0.14
35 | Phase 2 - Initiation | -0.03
35 | Phase 3 - Implementation | -0.11
35 | Phase 4 - Manufacturing | -0.01
36 | Phase 1 - Planning | -0.04
36 | Phase 2 - Initiation | -0.05
36 | Phase 3 - Implementation | -0.07
36 | Phase 4 - Manufacturing | -0.12
37 | Phase 1 - Planning | -0.11
37 | Phase 2 - Initiation | -0.08
37 | Phase 3 - Implementation | 0
37 | Phase 4 - Manufacturing | -0.14
38 | Phase 1 - Planning | -0.07
38 | Phase 2 - Initiation | -0.14
38 | Phase 3 - Implementation | -0.11
38 | Phase 4 - Manufacturing | -0.13
39 | Phase 1 - Planning | -0.14
39 | Phase 2 - Initiation | -0.05
39 | Phase 3 - Implementation | -0.13
39 | Phase 4 - Manufacturing | -0.03
40 | Phase 1 - Planning | -0.05
40 | Phase 2 - Initiation | -0.08
40 | Phase 3 - Implementation | -0.05
40 | Phase 4 - Manufacturing | -0.01
41 | Phase 1 - Planning | -0.02
41 | Phase 2 - Initiation | -0.13
41 | Phase 3 - Implementation | -0.14
41 | Phase 4 - Manufacturing | -0.06
42 | Phase 1 - Planning | 0
42 | Phase 2 - Initiation | -0.12
42 | Phase 3 - Implementation | -0.13
42 | Phase 4 - Manufacturing | -0.06
43 | Phase 1 - Planning | 0
43 | Phase 2 - Initiation | -0.04
43 | Phase 3 - Implementation | -0.09
43 | Phase 4 - Manufacturing | -0.02
44 | Phase 1 - Planning | -0.01
44 | Phase 2 - Initiation | -0.11
44 | Phase 3 - Implementation | -0.01
44 | Phase 4 - Manufacturing | -0.03
45 | Phase 1 - Planning | -0.06
45 | Phase 2 - Initiation | -0.14
45 | Phase 3 - Implementation | -0.06
45 | Phase 4 - Manufacturing | -0.12
46 | Phase 1 - Planning | -0.07
46 | Phase 2 - Initiation | -0.06
46 | Phase 3 - Implementation | 0
46 | Phase 4 - Manufacturing | -0.12
47 | Phase 1 - Planning | -0.1
47 | Phase 2 - Initiation | -0.12
47 | Phase 3 - Implementation | -0.05
47 | Phase 4 - Manufacturing | -0.05
48 | Phase 1 - Planning | -0.14
48 | Phase 2 - Initiation | -0.03
48 | Phase 3 - Implementation | -0.11
48 | Phase 4 - Manufacturing | -0.01
49 | Phase 1 - Planning | -0.04
49 | Phase 2 - Initiation | -0.05
49 | Phase 3 - Implementation | -0.07
49 | Phase 4 - Manufacturing | -0.12
50 | Phase 1 - Planning | -0.11
50 | Phase 2 - Initiation | -0.08
50 | Phase 3 - Implementation | 0
50 | Phase 4 - Manufacturing | -0.14
51 | Phase 1 - Planning | -0.07
51 | Phase 2 - Initiation | -0.14
51 | Phase 3 - Implementation | -0.11
51 | Phase 4 - Manufacturing | -0.13
52 | Phase E - Deployment | -0.14
52 | Phase C - Development | -0.05
52 | Phase A - Initiation | -0.13
52 | Phase F - Post-deployment | -0.03
52 | Phase B - Preparation | -0.12
52 | Phase D - Testing | -0.08
53 | Phase E - Deployment | -0.04
53 | Phase C - Development | 0
53 | Phase A - Initiation | -0.06
53 | Phase F - Post-deployment | -0.04
53 | Phase B - Preparation | -0.13
53 | Phase D - Testing | -0.07
54 | Phase E - Deployment | -0.12
54 | Phase C - Development | -0.09
54 | Phase A - Initiation | -0.11
54 | Phase F - Post-deployment | -0.15
54 | Phase B - Preparation | -0.09
54 | Phase D - Testing | -0.15
55 | Phase E - Deployment | -0.07
55 | Phase C - Development | 0
55 | Phase A - Initiation | -0.07
55 | Phase F - Post-deployment | -0.03
55 | Phase B - Preparation | -0.13
55 | Phase D - Testing | -0.14
56 | Phase E - Deployment | -0.1
56 | Phase C - Development | -0.03
56 | Phase A - Initiation | 0
56 | Phase F - Post-deployment | -0.12
56 | Phase B - Preparation | -0.12
56 | Phase D - Testing | -0.09
57 | Phase E - Deployment | -0.09
57 | Phase C - Development | -0.01
57 | Phase A - Initiation | -0.11
57 | Phase F - Post-deployment | -0.11
57 | Phase B - Preparation | -0.04
57 | Phase D - Testing | -0.12
58 | Phase E - Deployment | -0.15
58 | Phase C - Development | -0.15
58 | Phase A - Initiation | -0.04
58 | Phase F - Post-deployment | -0.12
58 | Phase B - Preparation | -0.01
58 | Phase D - Testing | -0.12
59 | Phase E - Deployment | -0.05
59 | Phase C - Development | -0.04
59 | Phase A - Initiation | -0.05
59 | Phase F - Post-deployment | -0.14
59 | Phase B - Preparation | -0.06
59 | Phase D - Testing | -0.09
60 | Phase E - Deployment | -0.03
60 | Phase C - Development | -0.03
60 | Phase A - Initiation | -0.13
60 | Phase F - Post-deployment | -0.07
60 | Phase B - Preparation | 0
60 | Phase D - Testing | 0
61 | Phase E - Deployment | -0.02
61 | Phase C - Development | -0.04
61 | Phase A - Initiation | -0.12
61 | Phase F - Post-deployment | -0.08
61 | Phase B - Preparation | -0.04
61 | Phase D - Testing | 0
62 | Phase E - Deployment | -0.06
62 | Phase C - Development | -0.04
62 | Phase A - Initiation | -0.13
62 | Phase F - Post-deployment | -0.07
62 | Phase B - Preparation | -0.12
62 | Phase D - Testing | -0.09
63 | Phase E - Deployment | -0.11
63 | Phase C - Development | -0.15
63 | Phase A - Initiation | -0.09
63 | Phase F - Post-deployment | -0.15
63 | Phase B - Preparation | -0.07
63 | Phase D - Testing | 0
64 | Phase E - Deployment | -0.07
64 | Phase C - Development | -0.03
64 | Phase A - Initiation | -0.13
64 | Phase F - Post-deployment | -0.14
64 | Phase B - Preparation | -0.1
64 | Phase D - Testing | -0.03
65 | Phase E - Deployment | 0
65 | Phase C - Development | -0.12
65 | Phase A - Initiation | -0.12
65 | Phase F - Post-deployment | -0.09
65 | Phase B - Preparation | -0.09
65 | Phase D - Testing | -0.01
66 | Phase E - Deployment | -0.11
66 | Phase C - Development | -0.11
66 | Phase A - Initiation | -0.04
66 | Phase F - Post-deployment | -0.12
66 | Phase B - Preparation | -0.15
66 | Phase D - Testing | -0.15
67 | Phase E - Deployment | -0.04
67 | Phase C - Development | -0.12
67 | Phase A - Initiation | -0.01
67 | Phase F - Post-deployment | -0.12
67 | Phase B - Preparation | -0.05
67 | Phase D - Testing | -0.04
68 | Phase E - Deployment | -0.05
68 | Phase C - Development | -0.14
68 | Phase A - Initiation | -0.06
68 | Phase F - Post-deployment | -0.09
68 | Phase B - Preparation | -0.03
68 | Phase D - Testing | -0.03
69 | Phase E - Deployment | -0.13
69 | Phase C - Development | -0.07
69 | Phase A - Initiation | 0
69 | Phase F - Post-deployment | 0
69 | Phase B - Preparation | -0.02
69 | Phase D - Testing | -0.04
70 | Phase E - Deployment | -0.12
70 | Phase C - Development | -0.08
70 | Phase A - Initiation | -0.04
70 | Phase F - Post-deployment | 0
70 | Phase B - Preparation | -0.06
70 | Phase D - Testing | -0.04
71 | Phase E - Deployment | -0.13
71 | Phase C - Development | -0.07
71 | Phase A - Initiation | -0.12
71 | Phase F - Post-deployment | -0.09
71 | Phase B - Preparation | -0.11
71 | Phase D - Testing | -0.15
72 | Phase E - Deployment | -0.09
72 | Phase C - Development | -0.15
72 | Phase A - Initiation | -0.07
72 | Phase F - Post-deployment | 0
72 | Phase B - Preparation | -0.07
72 | Phase D - Testing | -0.03
73 | Phase E - Deployment | -0.13
73 | Phase C - Development | -0.14
73 | Phase A - Initiation | -0.1
73 | Phase F - Post-deployment | -0.03
73 | Phase B - Preparation | 0
73 | Phase D - Testing | -0.12
74 | Phase E - Deployment | -0.12
74 | Phase C - Development | -0.09
74 | Phase A - Initiation | -0.09
74 | Phase F - Post-deployment | -0.01
74 | Phase B - Preparation | -0.11
74 | Phase D - Testing | -0.11
75 | Phase E - Deployment | -0.04
75 | Phase C - Development | -0.12
75 | Phase A - Initiation | -0.15
75 | Phase F - Post-deployment | -0.15
75 | Phase B - Preparation | -0.04
75 | Phase D - Testing | -0.12
76 | Phase E - Deployment | -0.01
76 | Phase C - Development | -0.12
76 | Phase A - Initiation | -0.05
76 | Phase F - Post-deployment | -0.04
76 | Phase B - Preparation | -0.05
76 | Phase D - Testing | -0.14
77 | Phase E - Deployment | -0.06
77 | Phase C - Development | -0.09
77 | Phase A - Initiation | -0.03
77 | Phase F - Post-deployment | -0.03
77 | Phase B - Preparation | -0.13
77 | Phase D - Testing | -0.07
78 | Phase E - Deployment | 0
78 | Phase C - Development | 0
78 | Phase A - Initiation | -0.02
78 | Phase F - Post-deployment | -0.04
78 | Phase B - Preparation | -0.42
78 | Phase D - Testing | -0.38
79 | Phase E - Deployment | -0.34
79 | Phase C - Development | -0.3
79 | Phase A - Initiation | -0.36
79 | Phase F - Post-deployment | -0.34
79 | Phase B - Preparation | -0.43
79 | Phase D - Testing | -0.37
80 | Phase E - Deployment | -0.42
80 | Phase C - Development | -0.39
80 | Phase A - Initiation | -0.41
80 | Phase F - Post-deployment | -0.45
80 | Phase B - Preparation | -0.39
80 | Phase D - Testing | -0.45
81 | Phase E - Deployment | -0.37
81 | Phase C - Development | -0.3
81 | Phase A - Initiation | -0.37
81 | Phase F - Post-deployment | -0.33
81 | Phase B - Preparation | -0.43
81 | Phase D - Testing | -0.44
82 | Phase E - Deployment | -0.4
82 | Phase C - Development | -0.33
82 | Phase A - Initiation | -0.3
82 | Phase F - Post-deployment | -0.42
82 | Phase B - Preparation | -0.42
82 | Phase D - Testing | -0.39
83 | Phase E - Deployment | -0.39
83 | Phase C - Development | -0.31
83 | Phase A - Initiation | -0.41
83 | Phase F - Post-deployment | -0.41
83 | Phase B - Preparation | -0.34
83 | Phase D - Testing | -0.42
84 | Phase E - Deployment | -0.45
84 | Phase C - Development | -0.45
84 | Phase A - Initiation | -0.34
84 | Phase F - Post-deployment | -0.42
84 | Phase B - Preparation | -0.31
84 | Phase D - Testing | -0.42
85 | Phase E - Deployment | -0.35
85 | Phase C - Development | -0.34
85 | Phase A - Initiation | -0.35
85 | Phase F - Post-deployment | -0.44
85 | Phase B - Preparation | -0.36
85 | Phase D - Testing | -0.39
86 | Phase E - Deployment | -0.33
86 | Phase C - Development | -0.33
86 | Phase A - Initiation | -0.43
86 | Phase F - Post-deployment | -0.37
86 | Phase B - Preparation | -0.3
86 | Phase D - Testing | -0.3
87 | Phase E - Deployment | -0.32
87 | Phase C - Development | -0.34
87 | Phase A - Initiation | -0.12
87 | Phase F - Post-deployment | -0.08
87 | Phase B - Preparation | -0.04
87 | Phase D - Testing | 0
88 | Phase E - Deployment | -0.06
88 | Phase C - Development | -0.04
88 | Phase A - Initiation | -0.13
88 | Phase F - Post-deployment | -0.07
88 | Phase B - Preparation | -0.12
88 | Phase D - Testing | -0.09
89 | Phase E - Deployment | -0.11
89 | Phase C - Development | -0.15
89 | Phase A - Initiation | -0.09
89 | Phase F - Post-deployment | -0.15
89 | Phase B - Preparation | -0.07
89 | Phase D - Testing | 0
90 | Phase E - Deployment | -0.07
90 | Phase C - Development | -0.03
90 | Phase A - Initiation | -0.13
90 | Phase F - Post-deployment | -0.14
90 | Phase B - Preparation | -0.1
90 | Phase D - Testing | -0.03
91 | Phase E - Deployment | 0
91 | Phase C - Development | -0.12
91 | Phase A - Initiation | -0.12
91 | Phase F - Post-deployment | -0.09
91 | Phase B - Preparation | -0.09
91 | Phase D - Testing | -0.01
92 | Phase E - Deployment | -0.11
92 | Phase C - Development | -0.11
92 | Phase A - Initiation | -0.04
92 | Phase F - Post-deployment | -0.12
92 | Phase B - Preparation | -0.15
92 | Phase D - Testing | -0.15
93 | Phase E - Deployment | -0.04
93 | Phase C - Development | -0.12
93 | Phase A - Initiation | -0.01
93 | Phase F - Post-deployment | -0.12
93 | Phase B - Preparation | -0.05
93 | Phase D - Testing | -0.04
94 | Phase E - Deployment | -0.05
94 | Phase C - Development | -0.14
94 | Phase A - Initiation | -0.06
94 | Phase F - Post-deployment | -0.09
94 | Phase B - Preparation | -0.03
94 | Phase D - Testing | -0.03
95 | Phase E - Deployment | -0.13
95 | Phase C - Development | -0.07
95 | Phase A - Initiation | 0
95 | Phase F - Post-deployment | 0
95 | Phase B - Preparation | -0.02
95 | Phase D - Testing | -0.04
96 | Phase E - Deployment | -0.12
96 | Phase C - Development | -0.08
96 | Phase A - Initiation | -0.04
96 | Phase F - Post-deployment | 0
96 | Phase B - Preparation | -0.06
96 | Phase D - Testing | -0.04
97 | Phase E - Deployment | -0.13
97 | Phase C - Development | -0.07
97 | Phase A - Initiation | -0.12
97 | Phase F - Post-deployment | -0.09
97 | Phase B - Preparation | -0.11
97 | Phase D - Testing | -0.15
98 | Phase E - Deployment | -0.09
98 | Phase C - Development | -0.15
98 | Phase A - Initiation | -0.07
98 | Phase F - Post-deployment | 0
98 | Phase B - Preparation | -0.07
98 | Phase D - Testing | -0.03
99 | Phase E - Deployment | -0.13
99 | Phase C - Development | -0.14
99 | Phase A - Initiation | -0.1
99 | Phase F - Post-deployment | -0.03
99 | Phase B - Preparation | 0
99 | Phase D - Testing | -0.12
100 | Phase E - Deployment | -0.12
100 | Phase C - Development | -0.09
100 | Phase A - Initiation | -0.09
100 | Phase F - Post-deployment | -0.01
100 | Phase B - Preparation | -0.11
100 | Phase D - Testing | -0.11
101 | Phase E - Deployment | -0.04
101 | Phase C - Development | -0.12
101 | Phase A - Initiation | -0.15
101 | Phase F - Post-deployment | -0.15
101 | Phase B - Preparation | -0.04
101 | Phase D - Testing | -0.12
102 | Phase E - Deployment | -0.01
102 | Phase C - Development | -0.12
102 | Phase A - Initiation | -0.05
102 | Phase F - Post-deployment | -0.04
102 | Phase B - Preparation | -0.05
102 | Phase D - Testing | -0.14
103 | Phase E - Deployment | -0.06
103 | Phase C - Development | -0.09
103 | Phase A - Initiation | -0.03
103 | Phase F - Post-deployment | -0.03
103 | Phase B - Preparation | -0.13
103 | Phase D - Testing | -0.07
104 | Phase 1 - Planning | 0
104 | Phase 2 - Initiation | 0
104 | Phase 3 - Implementation | -0.02
104 | Phase 4 - Manufacturing | -0.04

## Projects_Locations
Project_ID | Country
1 | Equateur
2 | France
3 | Liban
4 | Egypte
5 | Afrique du Sud
6 | Albanie
7 | Hollande
8 | Allemagne
9 | Belgique
10 | Benin
11 | Italie
12 | Hongrie
13 | Malaysie
14 | Croatie
15 | Burkina Faso
16 | Cote d'Ivoire
17 | Espagne
18 | Gabon
19 | Republique Chèque
20 | Colombie
21 | Estonie
22 | Bresil
23 | Suisse
24 | Ukraine
25 | Togo
26 | Japon
27 | La Reunion
28 | Russie
29 | Indonesie
30 | Canada
31 | Chine
32 | Turquie
33 | Malte
34 | Israel
35 | Norvege
36 | Portugal
37 | Pologne
38 | Grece
39 | Danemark
40 | Senegal
41 | Slovaquie
42 | Lituanie
43 | Luxembourg
44 | Jordanie
45 | Gambie
46 | Macedoine
47 | Niger
48 | Slovenie
49 | Ile Maurice
50 | Serbie
51 | Suede
52 | France
53 | Belgique
54 | Hollande
55 | Luxembourg
56 | Italie
57 | Japon
58 | Espagne
59 | Hongrie
60 | Pologne
61 | Republique Chèque
62 | Slovaquie
63 | Allemagne
64 | Serbie
65 | Croatie
66 | Slovenie
67 | Macedoine
68 | Albanie
69 | Canada
70 | Malte
71 | Turquie
72 | Grece
73 | Portugal
74 | Ukraine
75 | Russie
76 | Bielorussie
77 | Lituanie
78 | Estonie
79 | Suede
80 | Danemark
81 | Norvege
82 | Suisse
83 | Cote d'Ivoire
84 | Senegal
85 | Afrique du Sud
86 | Gambie
87 | Gabon
88 | Benin
89 | Togo
90 | Burkina Faso
91 | Niger
92 | Liban
93 | Jordanie
94 | Israel
95 | Egypte
96 | Colombie
97 | Bresil
98 | Equateur
99 | Indonesie
100 | Malaysie
101 | Chine
102 | Ile Maurice
103 | La Reunion
104 | Bielorussie

## Country_Profiles
Country | Region | Type
France | Western Europe | Affiliate
Belgique | Western Europe | Affiliate
Hollande | Western Europe | Affiliate
Luxembourg | Western Europe | Affiliate
Italie | Western Europe | Affiliate
Japon | Asia Pacific | Affiliate
Espagne | Western Europe | Affiliate
Hongrie | Central/Eastern Europe-Middle East-Africa | Affiliate
Pologne | Central/Eastern Europe-Middle East-Africa | Affiliate
Republique Chèque | Central/Eastern Europe-Middle East-Africa | Affiliate
Slovaquie | Central/Eastern Europe-Middle East-Africa | Affiliate
Allemagne | Western Europe | Affiliate
Serbie | Central/Eastern Europe-Middle East-Africa | Affiliate
Croatie | Central/Eastern Europe-Middle East-Africa | Affiliate
Slovenie | Central/Eastern Europe-Middle East-Africa | Affiliate
Macedoine | Central/Eastern Europe-Middle East-Africa | Distributor
Albanie | Central/Eastern Europe-Middle East-Africa | Distributor
Canada | North and Latin America | Distributor
Malte | Central/Eastern Europe-Middle East-Africa | Distributor
Turquie | Central/Eastern Europe-Middle East-Africa | Distributor
Grece | Western Europe | Affiliate
Portugal | Western Europe | Distributor
Ukraine | Central/Eastern Europe-Middle East-Africa | Affiliate
Russie | Central/Eastern Europe-Middle East-Africa | Affiliate
Bielorussie | Central/Eastern Europe-Middle East-Africa | Distributor
Lituanie | Central/Eastern Europe-Middle East-Africa | Affiliate
Estonie | Central/Eastern Europe-Middle East-Africa | Affiliate
Suede | Western Europe | Distributor
Danemark | Western Europe | Distributor
Norvege | Western Europe | Distributor
Suisse | Western Europe | Affiliate
Cote d'Ivoire | Central/Eastern Europe-Middle East-Africa | Distributor
Senegal | Central/Eastern Europe-Middle East-Africa | Distributor
Afrique du Sud | Central/Eastern Europe-Middle East-Africa | Distributor
Gambie | Central/Eastern Europe-Middle East-Africa | Distributor
Gabon | Central/Eastern Europe-Middle East-Africa | Distributor
Benin | Central/Eastern Europe-Middle East-Africa | Distributor
Togo | Central/Eastern Europe-Middle East-Africa | Distributor
Burkina Faso | Central/Eastern Europe-Middle East-Africa | Distributor
Niger | Central/Eastern Europe-Middle East-Africa | Distributor
Liban | Central/Eastern Europe-Middle East-Africa | Distributor
Jordanie | Central/Eastern Europe-Middle East-Africa | Distributor
Israel | Central/Eastern Europe-Middle East-Africa | Distributor
Egypte | Central/Eastern Europe-Middle East-Africa | Distributor
Colombie | North and Latin America | Distributor
Bresil | North and Latin America | Distributor
Equateur | North and Latin America | Affiliate
Indonesie | Asia Pacific | Distributor
Malaysie | Asia Pacific | Affiliate
Chine | Asia Pacific | Distributor
Ile Maurice | Central/Eastern Europe-Middle East-Africa | Distributor
La Reunion | Central/Eastern Europe-Middle East-Africa | Affiliate

## Dictionary
Nom du champ | Description | Type de données
Project_ID | Identifiant unique pour chaque projet. Dans ce jeu de données, chaque ligne représente une phase unique, et non un projet unique. Il y a donc plusieurs lignes pour chaque ID de projet | String
Project Type | Le type du projet (c'est-à-dire, IT ou marketing dans les données qui nous ont été transmises) | String
Country | Le pays dans lequel le projet est réalisé. | String
Phase | La phase du projet. Toutes les données relatives au projet (par exemple, les coûts, la deadline, les livrables, etc.) se rapportent à la phase spécifiée du projet. | String
Start Date | La date réelle à laquelle la phase projet a démarrée. Cette donnée est renseignée après le démarrage de la phase projet par l'équipe projet. | Datetime Object/Timestamp
Actual_Duration | Le nombre de jours constaté qui ont été nécessaires pour achever la phase du projet. Cette donnée est renseignée à l'issue de la phase du projet en question par l'équipe projet. | Float
Actual_Cost | Le coût (en USD) réel constaté de la phase spécifiée du projet. Cette donnée est renseignée à l'issue de la phase du projet en question par l'équipe projet et le contrôle de gestion. | Float
Planned_Duration | Le nombre de jours prévus pour achever la phase du projet. Cette donnée est une estimation renseignée par l'équipe projet avant le démarrage du projet à des fins de planification des ressources. | Float
Planned_Cost | Le coût prévu (en USD) pour achever les tâches du projet pour la phase de projet spécifiée. Cette donnée est une estimation renseignée par l'équipe projet avant le démarrage du projet à des fins de planification des ressources. | Float
Var_Deliverables | La différence en pourcentage entre le nombre cible de livrables et le nombre réel de livrables pour la phase de projet spécifiée. Cette donnée est renseignée à la fin de chaque phase projet à des fins de suivi de performance. Elle permet de tracer la quantité d'éléments qui auraient du être livrés par l'équipe projet au client interne mais qui ne l'ont pas été (exemple de livrables pour un projet IT : manuel utilisateur, gamme de test etc. exemple de livrables pour un projet marketing : rapport de benchmark de la concurrence...). A noter 0,15 signifie 15 % | Float
Country | Le pays dans lequel le projet est en cours de réalisation | String
Region | La région dont le pays fait partie. | String
Type | La classification du pays en fonction du type de partenariat (c'est-à-dire affilié ou distributeur). | String